## Durga Devi
Daily Plan Report — Durga Devi ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
BOQ software | Creation of new features and debugging | 10:00 | 12:00 | 120 min | approved | PMS
Project management software | PMS spliting the files to ensure the data performances and fixing | 12:00 | 14:00 | 120 min | approved | PMS
Site Management app | Database connection and Development | 14:30 | 16:00 | 90 min | approved | PMS
Payroll Management | Updates of application and debugging | 16:00 | 17:00 | 60 min | approved | PMS
Human Resource Management System | Requirements Analysis & System Architecture | 17:15 | 19:00 | 105 min | approved | PMS
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
Payroll Management | Debugging and updates ¦ added new sandwich deduction and punch timings deduction in payroll calculation ¦ Implemented sandwich leave and punch timing deductions in payroll calculations to automate policy-based salary deductions and improve payroll accuracy. | — | — | — | approved | Manual
Project management software | PMS spliting the files to ensure the data performances and fixing | 10:00 | 12:00 | 120 min | approved | PMS
Payroll Management | Updates of application and debugging | 12:00 | 14:00 | 120 min | approved | PMS
BOQ software | Creation of new features and debugging | 14:30 | 16:00 | 90 min | approved | PMS
Site Management app | Database connection and Development | 16:00 | 17:00 | 60 min | approved | PMS
Human Resource Management System | Requirements Analysis & System Architecture | 17:15 | 19:00 | 105 min | approved | PMS
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
Project management software | PMS spliting the files to ensure the data performances and fixing | 09:30 | 11:00 | 90 min | approved | PMS
Human Resource Management System | Requirements Analysis & System Architecture | 11:00 | 12:45 | 105 min | approved | PMS
Payroll Management | Debugging and updates | 12:45 | 14:00 | 75 min | approved | PMS
BOQ software | Creation of new features and debugging | 14:30 | 16:00 | 90 min | approved | PMS
Timeguard-Monitoring system | Creation of Mac Desktop Agent | 16:00 | 17:00 | 60 min | approved | PMS
Sketch a plan -Mobile appliation | Debugging and Updates | 17:15 | 18:30 | 75 min | approved | PMS
Site Management app | Database connection and Development | 18:30 | 19:00 | 30 min | approved | PMS
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
Project management software | PMS spliting the files to ensure the data performances and fixing | 10:00 | 12:00 | 120 min | approved | PMS
Payroll Management | Refinement of payroll page with updates | 12:00 | 14:00 | 120 min | approved | PMS
Human Resource Management System | Requirements Analysis & System Architecture | 14:30 | 16:00 | 90 min | approved | PMS
Payroll Management | Updates of application and debugging | 16:00 | 17:00 | 60 min | approved | PMS
Payroll Management | Debugging and updates | 17:15 | 18:00 | 45 min | approved | PMS
Timeguard-Monitoring system | Creation of Mac Desktop Agent | 18:00 | 19:00 | 60 min | approved | PMS
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
Project management software | PMS spliting the files to ensure the data performances and fixing | 10:00 | 12:00 | 120 min | approved | PMS
Payroll Management | Refinement of payroll page with updates | 12:00 | 14:00 | 120 min | approved | PMS
Site Management app | Database connection and Development | 14:00 | 16:00 | 120 min | approved | PMS
BOQ software | Creation of new features and debugging | 16:00 | 17:00 | 60 min | approved | PMS
Timeguard-Monitoring system | Creation of Mac Desktop Agent | 17:15 | 19:00 | 105 min | approved | PMS
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## Mohanraj C
Daily Plan Report — Mohanraj C ¦ July 6–10, 2026
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
Vendor Bills Reconciliation 2026-27 | Reconciliation of vendor bills against Zoho books Apr-May 2026 | 10:00 | 11:00 | 60 min | approved | PMS
TDS Reconciliation FY 2025-26 – SGK Auditors | TDS Reconciliation & Verification – FY 2025-26 with SGK Auditors | 11:15 | 14:00 | 165 min | approved | PMS
Sales invoice Raising 2026-27 | Verification of SL interior Measurement sheet | 14:30 | 17:00 | 150 min | approved | PMS
Vendor Payment | Verification of Vendor Payment Apr-Jul 2026 | 17:15 | 19:00 | 105 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
GST Filing 2026-27 | GSTR verification, reconciliation & filing of Jun 2026 | 10:00 | 11:00 | 60 min | approved | PMS
Bank Statement reconciliation CTI ICICI 2025-26 | ICICI Bank Statement Analysis and Excel Working - CTI 2026 | 11:15 | 14:00 | 165 min | approved | PMS
Finance Project Report 2026-27 | Reconciliation of project wise report against Zoho Books CTI Jun 2026 | 14:30 | 17:00 | 150 min | approved | PMS
Vendor Bills Reconciliation 2026-27 | Reconciliation of vendor bills against Zoho books Apr-May 2026 | 17:15 | 19:00 | 105 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
BOQ working - CTI and KPL | BOQ Preparation, Review & Cost Estimation – CTI & KPL ¦ ¦ Prepared, reviewed, and verified BOQs for CTI and KPL projects, including quantity take-off, cost estimation, and validation of material and labour requirements to support project execution and quotation preparation. | — | — | — | approved | Manual
Sales invoice Raising 2026-27 | Hexaware Sales Invoice Creation ¦ ¦ Prepared estimates and created sales invoices for Hexaware projects by verifying project details, purchase orders, and billing requirements, ensuring accurate and timely invoice generation. | — | — | — | approved | Manual
OD Registration Coordination – HDFC & Finance Limited | OD Registration Coordination, Documentation & Follow-up – HDFC & Finance Limited ¦ ¦ Coordinated the OD registration process with HDFC Bank and Finance Limited by reviewing documentation requirements, verifying submitted records, and following up with stakeholders to facilitate timely approval and completion of the registration process. | — | — | — | approved | Manual
GST Filing 2026-27 | Analysis & working of GSTR filing Jun 2026 ¦ ¦ Performed analysis and working for GSTR filing for June 2026 by verifying GST transactions, reconciling records with Zoho Books, resolving discrepancies, and preparing the data for accurate GST filing. | — | — | — | approved | Manual
Project name Creation in Zoho Books - CTI & KPL | Zoho Books Project Setup & Creation – CTI & KPL ¦ ¦ Created and configured project names in Zoho Books for CTI and KPL by updating customer details, project information, and financial tracking parameters to support accurate project accounting and reporting. | — | — | — | approved | Manual
Bank Statement reconciliation CTI ICICI 2025-26 | Analysis of HDFC Bank Statement - CTI 2025-26 | 10:00 | 11:00 | 60 min | approved | PMS
Bank Statement reconciliation CTI ICICI 2025-26 | Analysis of ICICI Bank Statement - CTI 2025-26 | 11:15 | 14:00 | 165 min | approved | PMS
ICICI, HDFC & KVB Bank Statement Category Working | Bank Statement Categorization & Verification – ICICI, HDFC & KVB | 14:30 | 17:00 | 150 min | approved | PMS
Monthly Budget Forecasting 2026-27 | Budget Analysis for the month of July 2026 | 17:15 | 19:00 | 105 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
ICICI, HDFC & KVB Bank Statement Category Working | Bank Statement Categorization & Verification – ICICI, HDFC & KVB | 10:00 | 11:00 | 60 min | approved | PMS
MD Cabin Setup | CDW - Quotation revision | 11:15 | 14:00 | 165 min | approved | PMS
Vendor Payment | Verification of Vendor Payment Apr-Jul 2026 | 14:30 | 17:00 | 150 min | approved | PMS
Sales invoice Raising 2026-27 | Verification of SL interior Measurement sheet | 17:15 | 19:00 | 105 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## Pushpa Prithviraj
Daily Plan Report — Pushpa Prithviraj ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | — | — | — | pending | Manual
HR Operations | Vendor Follow-up for Housekeeping Services | 17:15 | 17:45 | 30 min | approved | PMS
Pay sheet | Alphaori Attendance Sheet Preparation | 17:45 | 18:15 | 30 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 18:15 | 18:45 | 30 min | approved | PMS
HR Operations | DA and Professional Tax Data Collection | 18:45 | 19:15 | 30 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 19:15 | 19:45 | 30 min | approved | PMS
Professional Tax Registration | Follow up for Registration with Auditor/Relevant Authority | 19:45 | 20:15 | 30 min | approved | PMS
HR Operations | HR Position Interview | 20:15 | 20:45 | 30 min | approved | PMS
HR Operations | Meeting with sam sir | 20:45 | 21:15 | 30 min | approved | PMS
Workforce Productivity Tracking Initiative | Monitor and analyze employee attendance and productivity data to improve operational efficiency. | 21:15 | 21:45 | 30 min | approved | PMS
Talent acquisition | Procurement Role Candidate Identification | 21:45 | 22:15 | 30 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 22:15 | 22:45 | 30 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 22:45 | 23:15 | 30 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 23:15 | 23:45 | 30 min | approved | PMS
HR Operations | Roles and Responsibilities Template Communication | 23:45 | 23:59 | 15 min | approved | PMS
Hiring Interns | Screening Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Timesheet Review & Validation | 23:59 | 23:59 | 15 min | approved | PMS
Hiring Interns | Sourcing Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Site Engineer Hiring Initiative -100 | Sourcing profiles through job portals. | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
Pay sheet | LMS Update & Monitoring | — | — | — | pending | Manual
HR Operations | Vendor Follow-up for Housekeeping Services | 17:15 | 17:45 | 30 min | approved | PMS
Pay sheet | Alphaori Attendance Sheet Preparation | 17:45 | 18:15 | 30 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 18:15 | 18:45 | 30 min | approved | PMS
HR Operations | DA and Professional Tax Data Collection | 18:45 | 19:15 | 30 min | approved | PMS
HR Operations | Employee Appraisal Discussion Meeting | 19:15 | 19:45 | 30 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 19:45 | 20:15 | 30 min | approved | PMS
Professional Tax Registration | Follow up for Registration with Auditor/Relevant Authority | 20:15 | 20:45 | 30 min | approved | PMS
HR Operations | HR Position Interview | 20:45 | 21:15 | 30 min | approved | PMS
Talent acquisition | Job posting and creation | 21:15 | 21:45 | 30 min | approved | PMS
HR Operations | Meeting with sam sir | 21:45 | 22:15 | 30 min | approved | PMS
Workforce Productivity Tracking Initiative | Monitor and analyze employee attendance and productivity data to improve operational efficiency. | 22:15 | 22:45 | 30 min | approved | PMS
Talent acquisition | Procurement Role Candidate Identification | 22:45 | 23:15 | 30 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 23:15 | 23:45 | 30 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 23:45 | 23:59 | 15 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 23:59 | 23:59 | 15 min | approved | PMS
Hiring Interns | Screening Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 23:59 | 23:59 | 15 min | approved | PMS
Hiring Interns | Sourcing Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Timesheet Review & Validation | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
HR Operations | Offer Letter Preparation & Coordination | — | — | — | pending | Manual
Meet up with clients | Coordinated with Maya (Manager) | — | — | — | pending | Manual
HR Operations | Vendor Follow-up for Housekeeping Services | 17:15 | 17:45 | 30 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 17:45 | 18:15 | 30 min | approved | PMS
HR Operations | checked with different insurance agencies for employee group insurance | 18:15 | 18:45 | 30 min | approved | PMS
HR Operations | DA and Professional Tax Data Collection | 18:45 | 19:15 | 30 min | approved | PMS
HR Operations | Employee Appraisal Discussion Meeting | 19:15 | 19:45 | 30 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 19:45 | 20:15 | 30 min | approved | PMS
HR Operations | HR Position Interview | 20:15 | 20:45 | 30 min | approved | PMS
HR Operations | Meeting with sam sir | 20:45 | 21:15 | 30 min | approved | PMS
Workforce Productivity Tracking Initiative | Monitor and analyze employee attendance and productivity data to improve operational efficiency. | 21:15 | 21:45 | 30 min | approved | PMS
Talent acquisition | Procurement Role Candidate Identification | 21:45 | 22:15 | 30 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 22:15 | 22:45 | 30 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 22:45 | 23:15 | 30 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 23:15 | 23:45 | 30 min | approved | PMS
Hiring Interns | Screening Candidates | 23:45 | 23:59 | 15 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 23:59 | 23:59 | 15 min | approved | PMS
Hiring Interns | Sourcing Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Timesheet Review & Validation | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Verified the OT details before sending them to Sam Sir | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Meeting with sam sir | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
HR Operations | Vendor Follow-up for Housekeeping Services | 17:15 | 17:45 | 30 min | approved | PMS
Pay sheet | Attendance Data Analysis | 17:45 | 18:15 | 30 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 18:15 | 18:45 | 30 min | approved | PMS
HR Operations | DA and Professional Tax Data Collection | 18:45 | 19:15 | 30 min | approved | PMS
Professional Tax Registration | Follow up for Registration with Auditor/Relevant Authority | 19:15 | 19:45 | 30 min | approved | PMS
HR Operations | HR Position Interview | 19:45 | 20:15 | 30 min | approved | PMS
HR Operations | Meeting with sam sir | 20:15 | 20:45 | 30 min | approved | PMS
Workforce Productivity Tracking Initiative | Monitor and analyze employee attendance and productivity data to improve operational efficiency. | 20:45 | 21:15 | 30 min | approved | PMS
Talent acquisition | Procurement Role Candidate Identification | 21:15 | 21:45 | 30 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 21:45 | 22:15 | 30 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 22:15 | 22:45 | 30 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 22:45 | 23:15 | 30 min | approved | PMS
Hiring Interns | Screening Candidates | 23:15 | 23:45 | 30 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 23:45 | 23:59 | 15 min | approved | PMS
Hiring Interns | Sourcing Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Timesheet Review & Validation | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Verified the OT details before sending them to Sam Sir | 23:59 | 23:59 | 15 min | approved | PMS
Site Engineer Hiring Initiative -100 | Sourcing profiles through job portals. | 23:59 | 23:59 | 15 min | approved | PMS
HR Operations | Offer Letter Preparation & Coordination | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
HR Operations | Vendor Follow-up for Housekeeping Services | 17:15 | 17:45 | 30 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 17:45 | 18:15 | 30 min | approved | PMS
Meet up with clients | Client Relationship Management | 18:15 | 18:45 | 30 min | approved | PMS
Meet up with clients | Coordinated the ISON client meet-up to ensure smooth communication and successful execution . | 18:45 | 19:15 | 30 min | approved | PMS
Meet up with clients | Coordinated with Maya (Manager) | 19:15 | 19:45 | 30 min | approved | PMS
HR Operations | DA and Professional Tax Data Collection | 19:45 | 20:15 | 30 min | approved | PMS
Pay sheet | Edited the salary slips and sent them to all employees | 20:15 | 20:45 | 30 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 20:45 | 21:15 | 30 min | approved | PMS
HR Operations | HR Position Interview | 21:15 | 21:45 | 30 min | approved | PMS
HR Operations | Meeting with sam sir | 21:45 | 22:15 | 30 min | approved | PMS
Workforce Productivity Tracking Initiative | Monitor and analyze employee attendance and productivity data to improve operational efficiency. | 22:15 | 22:45 | 30 min | approved | PMS
Talent acquisition | Procurement Role Candidate Identification | 22:45 | 23:15 | 30 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 23:15 | 23:45 | 30 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 23:45 | 23:59 | 15 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 23:59 | 23:59 | 15 min | approved | PMS
Hiring Interns | Screening Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 23:59 | 23:59 | 15 min | approved | PMS
Hiring Interns | Sourcing Candidates | 23:59 | 23:59 | 15 min | approved | PMS
Pay sheet | Timesheet Review & Validation | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## Rebecasuji
Daily Plan Report — Rebecasuji ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
Timeguard-Monitoring system | Creation of Mac Desktop Agent | 10:00 | 11:30 | 90 min | approved | PMS
BOQ software | Creation of new features and debugging | 11:45 | 14:00 | 135 min | approved | PMS
Sketch a plan -Mobile appliation | Debugging and Updates | 14:30 | 16:00 | 90 min | approved | PMS
Project management software | PMS spliting the files to ensure the data performances and fixing | 16:00 | 18:00 | 120 min | approved | PMS
Human Resource Management System | Requirements Analysis & System Architecture | 18:00 | 19:00 | 60 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
Timeguard-Monitoring system | Creation of Mac Desktop Agent | 10:20 | 11:20 | 60 min | approved | PMS
BOQ software | Creation of new features and debugging | 11:30 | 14:00 | 150 min | approved | PMS
Sketch a plan -Mobile appliation | Debugging and Updates | 14:00 | 16:00 | 120 min | approved | PMS
Project management software | PMS spliting the files to ensure the data performances and fixing | 16:15 | 18:00 | 105 min | approved | PMS
Human Resource Management System | Requirements Analysis & System Architecture | 18:00 | 19:15 | 75 min | approved | PMS
Payroll Management | Updates of application and debugging | 20:15 | 20:45 | 30 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
BOQ software | Creation of new features and debugging | 10:15 | 12:15 | 120 min | approved | PMS
Site Management app | Database connection and Development | 12:30 | 14:00 | 90 min | approved | PMS
Sketch a plan -Mobile appliation | Debugging and Updates | 14:30 | 16:00 | 90 min | approved | PMS
Payroll Management | Debugging and updates | 16:00 | 19:15 | 195 min | approved | PMS
Project management software | PMS spliting the files to ensure the data performances and fixing | 19:15 | 19:45 | 30 min | approved | PMS
Human Resource Management System | Requirements Analysis & System Architecture | 19:45 | 20:15 | 30 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
LMS Project | Creation of new features | 10:30 | 11:40 | 70 min | approved | PMS
BOQ software | Creation of new features and debugging | 11:50 | 14:00 | 130 min | approved | PMS
Site Management app | Database connection and Development | 14:30 | 16:00 | 90 min | approved | PMS
Project management software | PMS spliting the files to ensure the data performances and fixing | 16:15 | 19:30 | 195 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## S.NAVEEN KUMAR
Daily Plan Report — S.NAVEEN KUMAR ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
Time88 web application | Time 88 project discussion | 10:00 | 11:15 | 75 min | approved | PMS
Time88 web application | App Suite Content Validation | 11:30 | 13:10 | 100 min | approved | PMS
Time88 web application | Performance Optimization | 13:10 | 14:10 | 60 min | approved | PMS
Time88 web application | Scroll-Based Card Animation | 14:40 | 17:30 | 170 min | approved | PMS
Time88 web application | App Suite Gradient Enhancement | 17:45 | 19:10 | 85 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:10 | 14:40 | 30 min | approved | Manual
Break | Evening Break | 17:30 | 17:45 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
Time88 web application | Time 88 project discussion | 10:00 | 11:15 | 75 min | approved | PMS
Time88 web application | Scroll-Based Card Animation | 11:30 | 14:10 | 160 min | approved | PMS
Time88 web application | Performance Optimization | 14:40 | 16:30 | 110 min | approved | PMS
Time88 web application | Hero Section Refinement | 16:30 | 17:30 | 60 min | approved | PMS
Time88 web application | App Suite Content Validation | 17:45 | 19:05 | 80 min | approved | PMS
Break | Morning Break | 11:15 | 11:30 | 15 min | approved | Manual
Break | Lunch | 14:10 | 14:40 | 30 min | approved | Manual
Break | Evening Break | 17:30 | 17:45 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
Sketch App | Plan Card Visual Structure Enhancement | 10:00 | 11:15 | 75 min | approved | PMS
Sketch App | Plan Count and Sort Row Alignment | 11:30 | 13:10 | 100 min | approved | PMS
Sketch App | Plan Listing Screen Reference Analysis | 13:10 | 14:10 | 60 min | approved | PMS
Sketch App | Divider and Section Separation | 14:40 | 16:30 | 110 min | approved | PMS
Sketch App | Device-Based Visual Verification | 16:30 | 17:30 | 60 min | approved | PMS
Sketch App | Compose Padding Build Error Resolution | 17:45 | 19:10 | 85 min | approved | PMS
Break | Morning Break | 11:15 | 11:30 | 15 min | approved | Manual
Break | Lunch | 14:10 | 14:40 | 30 min | approved | Manual
Break | Evening Break | 17:15 | 17:30 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
Sketch App | Status Filter Chip Redesign | 10:00 | 11:15 | 75 min | approved | PMS
Sketch App | Responsive Layout Validation | 11:30 | 13:10 | 100 min | approved | PMS
Sketch App | Project Subtitle Integration | 13:10 | 14:10 | 60 min | approved | PMS
Sketch App | Plan Listing Screen Reference Analysis | 14:40 | 16:30 | 110 min | approved | PMS
Sketch App | Device-Based Visual Verification | 16:30 | 17:30 | 60 min | approved | PMS
Sketch App | Compose Padding Build Error Resolution | 17:45 | 19:10 | 85 min | approved | PMS
Break | Morning Break | 11:15 | 11:30 | 15 min | approved | Manual
Break | Lunch | 14:10 | 14:40 | 30 min | approved | Manual
Break | Evening Break | 17:30 | 17:45 | 15 min | approved | Manual

## Samyuktha
Daily Plan Report — Samyuktha ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
Pay sheet | Marked daily attendance for all employees | — | — | — | pending | Manual
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | — | — | — | pending | Manual
Pay sheet | Marked daily attendance for all employees | 10:00 | 10:20 | 20 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 10:20 | 11:50 | 90 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 11:50 | 13:20 | 90 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 13:20 | 14:00 | 40 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 15:00 | 16:30 | 90 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 16:30 | 18:00 | 90 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 18:00 | 19:00 | 60 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
Pay sheet | Marked daily attendance for all employees | 10:00 | 10:20 | 20 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 10:20 | 11:50 | 90 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 11:50 | 13:20 | 90 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 13:20 | 14:00 | 40 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 14:40 | 16:30 | 110 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 16:30 | 18:00 | 90 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 18:00 | 19:00 | 60 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
Pay sheet | Marked daily attendance for all employees | 10:00 | 10:20 | 20 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 10:20 | 11:50 | 90 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 11:50 | 13:20 | 90 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 13:20 | 14:00 | 40 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 14:50 | 16:30 | 100 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 16:30 | 18:00 | 90 min | approved | PMS
Pay sheet | Edited the salary slips and sent them to all employees | 18:00 | 19:10 | 70 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
Pay sheet | Marked daily attendance for all employees | 09:50 | 10:10 | 20 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 10:10 | 11:40 | 90 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 11:40 | 13:10 | 90 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 13:10 | 14:00 | 50 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 14:40 | 16:20 | 100 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 16:20 | 17:50 | 90 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 17:50 | 19:00 | 70 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
Pay sheet | Marked daily attendance for all employees | 10:00 | 10:20 | 20 min | approved | PMS
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 10:20 | 11:50 | 90 min | approved | PMS
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 11:50 | 13:20 | 90 min | approved | PMS
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 13:20 | 14:00 | 40 min | approved | PMS
Talent acquisition | Production Operator Candidate Sourcing | 14:40 | 16:30 | 110 min | approved | PMS
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 16:30 | 18:00 | 90 min | approved | PMS
Pay sheet | Project entry and configuration in pms . | 18:00 | 19:10 | 70 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## Sivakumar
Daily Plan Report — Sivakumar ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 10:15 | 12:15 | 120 min | approved | PMS
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 12:15 | 14:15 | 120 min | approved | PMS
Phase 2 Restroom | Buffing of the Existing walls already painted with emulsion upto 11 feet till the bare plastering is visible | 17:15 | 18:15 | 60 min | approved | PMS
Phase 2 Restroom | 250mm Depth Floor chasing for Laying Pipes inside the restroom | 19:15 | 19:45 | 30 min | approved | PMS
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 19:45 | 20:15 | 30 min | approved | PMS
Phase 2 Restroom | Chiseling of the existing walls upto 11 ft in order to lay wall tiles | 20:15 | 20:45 | 30 min | approved | PMS
Phase 2 Restroom | Delivery of Sanitarywares and CP fittings | 20:45 | 21:15 | 30 min | approved | PMS
Phase 2 Restroom | Delivery of Tiles | 21:15 | 21:45 | 30 min | approved | PMS
Phase 2 Restroom | Excavation for Laying soil and waste water line upto 500mm depth | 21:45 | 22:15 | 30 min | approved | PMS
Phase 2 Restroom | Excavation for Manhole chamber | 22:15 | 22:45 | 30 min | approved | PMS
Phase 2 Restroom | Excavation required upto 1000mm | 22:45 | 23:15 | 30 min | approved | PMS
Phase 2 Restroom | Manhole chamber Construction | 23:15 | 23:45 | 30 min | approved | PMS
Phase 2 Restroom | Pest control | 23:45 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Phase 2 Restroom | Breaking of Connecting Beams | 15:15 | 17:15 | 120 min | approved | PMS
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
Phase 2 Restroom | 250mm Depth Floor chasing for Laying Pipes inside the restroom | 17:15 | 17:45 | 30 min | approved | PMS
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:45 | 18:15 | 30 min | approved | PMS
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 18:15 | 18:45 | 30 min | approved | PMS
Phase 2 Restroom | Concrete work | 19:15 | 19:45 | 30 min | approved | PMS
Customer Experience Centre Renovation | Acoustic Fabric Paneling | 19:45 | 20:15 | 30 min | approved | PMS
Customer Experience Centre Renovation | Plywood Support for TV | 20:15 | 20:45 | 30 min | approved | PMS
Phase 2 Restroom | Removal of Balance soil from Parking Area | 20:45 | 21:15 | 30 min | approved | PMS
Phase 2 Restroom | Side wall construction for Counters | 21:15 | 21:45 | 30 min | approved | PMS
Phase 2 Restroom | Water Stagnation Test | 21:45 | 22:15 | 30 min | approved | PMS
Phase 2 Restroom | Water Proofing | 22:15 | 22:45 | 30 min | approved | PMS
Phase 2 Restroom | Wall Construction as per approved drawing | 22:45 | 23:15 | 30 min | approved | PMS
Phase 2 Restroom | Wall Chesling | 23:15 | 23:45 | 30 min | approved | PMS
Phase 2 Restroom | Wall Chasing for Plumbing works | 23:45 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Wall chasing for Electrical conduits | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Tile details for procurement Wall and Floor | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Shuttering work | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Sanitaryware and CP fittings sample approval | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Rough Plastering | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
Phase 2 Restroom | Breaking of Connecting Beams | 18:45 | 19:15 | 30 min | approved | PMS
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:15 | 17:45 | 30 min | approved | PMS
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 17:45 | 18:15 | 30 min | approved | PMS
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 18:15 | 18:45 | 30 min | approved | PMS
Phase 2 Restroom | Buffing of the Existing walls already painted with emulsion upto 11 feet till the bare plastering is visible | 18:45 | 19:15 | 30 min | approved | PMS
Phase 2 Restroom | Create Items that are not part of BOQ - find qty and pricing | 19:15 | 19:45 | 30 min | approved | PMS
Phase 2 Restroom | Delivery of Sanitarywares and CP fittings | 19:45 | 20:15 | 30 min | approved | PMS
Phase 2 Restroom | Delivery of Tiles | 20:15 | 20:45 | 30 min | approved | PMS
Phase 2 Restroom | Excavation required upto 1000mm | 20:45 | 21:15 | 30 min | approved | PMS
Phase 2 Restroom | Getting Quotation details from vendor (pipes)-phase 2 | 21:15 | 21:45 | 30 min | approved | PMS
Phase 2 Restroom | PCC work after laying the floor concealed pipes | 21:45 | 22:15 | 30 min | approved | PMS
Phase 2 Restroom | Pest control | 22:15 | 22:45 | 30 min | approved | PMS
Phase 2 Restroom | Procurement of Sanitarywares and Fittings | 22:45 | 23:15 | 30 min | approved | PMS
Phase 2 Restroom | RCC laying underneath the floor cut area | 23:15 | 23:45 | 30 min | approved | PMS
Phase 2 Restroom | Removal of Balance soil from Parking Area | 23:45 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Removal of existing AC ducts and closing all supply and return | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Rough Plastering | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Sanitaryware and CP fitting sample approval | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Wall Chasing for Plumbing works | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Wall Chesling | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:15 | 17:45 | 30 min | approved | PMS
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 17:45 | 18:15 | 30 min | approved | PMS
Phase 2 Restroom | Electrical Cable laying (power cables) | 18:45 | 19:15 | 30 min | approved | PMS
Phase 2 Restroom | Electrical pipe laying | 19:15 | 19:45 | 30 min | approved | PMS
Phase 2 Restroom | Excavation required upto 1000mm | 19:45 | 20:15 | 30 min | approved | PMS
Phase 2 Restroom | Exhaust Ducts Installation | 20:15 | 20:45 | 30 min | approved | PMS
Phase 2 Restroom | Filling of Soil | 20:45 | 21:15 | 30 min | approved | PMS
Phase 2 Restroom | Filling Soil and Paver block Installation | 21:15 | 21:45 | 30 min | approved | PMS
EB 3 restroom renovation | Finalize the BOM for rest room project | 21:45 | 22:15 | 30 min | approved | PMS
Phase 2 Restroom | Laminate Shade/Design Confirmation | 22:15 | 22:45 | 30 min | approved | PMS
Phase 2 Restroom | Laying of inlet Pipe Line (Exterior) | 22:45 | 23:15 | 30 min | approved | PMS
Phase 2 Restroom | Laying of Soil water line outside Restroom | 23:15 | 23:45 | 30 min | approved | PMS
Customer Care Experience Centre Addnl | Termination of Sockets and switches | 23:45 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Tile details for procurement Wall and Floor | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Water Proofing | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Water Stagnation Test | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Wall Construction as per approved drawing | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Wall Chesling | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
Phase 2 Restroom | Breaking of Connecting Beams | 18:15 | 18:45 | 30 min | approved | PMS
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
SVP cabin | AC Power Installation | 17:15 | 17:45 | 30 min | approved | PMS
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:45 | 18:15 | 30 min | approved | PMS
Hexaware restroom renovation | BOQ PREPARATION FOR RESTROOMS | 18:15 | 18:45 | 30 min | approved | PMS
Phase 2 Restroom | Delivery of Sanitarywares and CP fittings | 18:45 | 19:15 | 30 min | approved | PMS
Phase 2 Restroom | Delivery of Tiles | 19:15 | 19:45 | 30 min | approved | PMS
Phase 2 Restroom | Electrical Cable laying (power cables) | 19:45 | 20:15 | 30 min | approved | PMS
Phase 2 Restroom | Excavation required upto 1000mm | 20:15 | 20:45 | 30 min | approved | PMS
Phase 2 Restroom | Excavation for Manhole chamber | 20:45 | 21:15 | 30 min | approved | PMS
Phase 2 Restroom | Exhaust Ducts Installation | 21:15 | 21:45 | 30 min | approved | PMS
Phase 2 Restroom | Filling of Soil | 21:45 | 22:15 | 30 min | approved | PMS
Phase 2 Restroom | Laying of 160mm Pipe line | 22:15 | 22:45 | 30 min | approved | PMS
Phase 2 Restroom | Laying of inlet Pipe Line (Exterior) | 22:45 | 23:15 | 30 min | approved | PMS
Phase 2 Restroom | Laying of pipes of water Inlet | 23:15 | 23:45 | 30 min | approved | PMS
Phase 2 Restroom | Laying of Soil water line outside Restroom | 23:45 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Manhole chamber Construction | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Pest control | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Rough Plastering | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Shuttering for Slab for mounting the Granite top for Wash basin | 23:59 | 23:59 | 15 min | approved | PMS
Phase 2 Restroom | Side wall construction for Counters | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## Sivaram C
Daily Plan Report — Sivaram C ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
DLF | Get Material and Labour Pricing from Vendors ¦ | — | — | — | approved | Manual
BOQ Products Adding | Create New Products for | 10:00 | 14:00 | 240 min | approved | PMS
BOQ Products Adding | Create New Products for Interior scope | 14:00 | 16:00 | 120 min | approved | PMS
BOQ Products Materials Creation | add new products | 16:00 | 18:15 | 135 min | approved | PMS
BOQ Products Materials Creation | Given Excel Material Adding BOQ | 18:45 | 19:15 | 30 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
BOQ Products Adding | Create New Products for | 10:30 | 14:30 | 240 min | approved | PMS
BOQ Products Adding | Create New Products for Interior scope | 17:45 | 18:15 | 30 min | approved | PMS
BOQ Products Materials Creation | add new products | 18:15 | 18:45 | 30 min | approved | PMS
BOQ Products Materials Creation | Given Excel Material Adding BOQ | 18:45 | 19:15 | 30 min | approved | PMS
BOQ Products Materials Creation | Materials collecting from AI | 19:15 | 19:45 | 30 min | approved | PMS
DLF | Get Material and Labour Pricing from Vendors | 19:45 | 20:15 | 30 min | approved | PMS
DLF | Get Material Details from Vendor | 20:15 | 20:45 | 30 min | approved | PMS
DLF | Prepare BOM | 20:45 | 21:15 | 30 min | approved | PMS
DLF | Prepare BOQ | 21:15 | 21:45 | 30 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
BOQ Products Adding | Create New Products for Interior scope | 10:00 | 14:00 | 240 min | approved | PMS
BOQ Products Adding | Create New Products for | 17:15 | 17:45 | 30 min | approved | PMS
BOQ Products Adding | Get Material and Labour Pricing from Vendors | 18:15 | 18:45 | 30 min | approved | PMS
BOQ Products Adding | Get Material Details from Vendor | 18:45 | 19:15 | 30 min | approved | PMS
BOQ Products Adding | Prepare BOM | 19:15 | 19:45 | 30 min | approved | PMS
BOQ Products Adding | Prepare BOQ | 19:45 | 20:15 | 30 min | approved | PMS
BOQ Products Materials Creation | add new products | 20:15 | 20:45 | 30 min | approved | PMS
BOQ Products Materials Creation | Get Material and Labour Pricing from Vendors | 20:45 | 21:15 | 30 min | approved | PMS
BOQ Products Materials Creation | Get Material Details from Vendor | 21:15 | 21:45 | 30 min | approved | PMS
BOQ Products Materials Creation | Given Excel Material Adding BOQ | 21:45 | 22:15 | 30 min | approved | PMS
BOQ Products Materials Creation | Prepare BOM | 22:45 | 23:15 | 30 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
CRECHE | Get Material and Labour Pricing from Vendors | 10:00 | 14:00 | 240 min | approved | PMS
CRECHE | Get Material Details from Vendor | 17:45 | 18:15 | 30 min | approved | PMS
CRECHE | Prepare BOM | 18:15 | 18:45 | 30 min | approved | PMS
CRECHE | Prepare BOQ | 18:45 | 19:15 | 30 min | approved | PMS
BOQ Products Adding | Create New Products for | 19:15 | 19:45 | 30 min | approved | PMS
BOQ Products Adding | Create New Products for Interior scope | 19:45 | 20:15 | 30 min | approved | PMS
BOQ Products Adding | Get Material and Labour Pricing from Vendors | 20:15 | 20:45 | 30 min | approved | PMS
BOQ Products Adding | Get Material Details from Vendor | 20:45 | 21:15 | 30 min | approved | PMS
BOQ Products Adding | Prepare BOM | 21:15 | 21:45 | 30 min | approved | PMS
BOQ Products Adding | Prepare BOQ | 21:45 | 22:15 | 30 min | approved | PMS
BOQ Products Materials Creation | Get Material Details from Vendor | 22:15 | 22:45 | 30 min | approved | PMS
BOQ Products Materials Creation | Given Excel Material Adding BOQ | 22:45 | 23:15 | 30 min | approved | PMS
BOQ Products Materials Creation | Materials collecting from AI | 23:15 | 23:45 | 30 min | approved | PMS
BOQ Products Materials Creation | Prepare BOM | 23:45 | 23:59 | 15 min | approved | PMS
BOQ Products Materials Creation | Prepare BOQ | 23:59 | 23:59 | 15 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## Yuvaraj
Daily Plan Report — Yuvaraj ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 10:00 | 12:30 | 150 min | approved | PMS
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 12:30 | 14:03 | 93 min | approved | PMS
General project | General task | 14:30 | 15:30 | 60 min | approved | PMS
Store Room Modificatoin at Featherlite | Get Material and Labour Pricing from Vendors | 15:30 | 17:00 | 90 min | approved | PMS
Store Room Modificatoin at Featherlite | Get Material Details from Vendor | 17:00 | 18:00 | 60 min | approved | PMS
CTI Maintenance | Material pricing and arrangements | 18:00 | 19:00 | 60 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 08:30 | 12:30 | 240 min | approved | PMS
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 12:30 | 14:00 | 90 min | approved | PMS
SVP cabin | all interior work | 14:30 | 18:30 | 240 min | approved | PMS
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 17:15 | 17:45 | 30 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:00 | 17:15 | 15 min | approved | Manual

## Zameela Begam
Daily Plan Report — Zameela Begam ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Duration | Status | Source
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 | 09:50 | 11:15 | 85 min | approved | PMS
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses | 11:30 | 14:05 | 155 min | approved | PMS
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing | 14:35 | 17:45 | 190 min | approved | PMS
New Company Registration | Processing of Time88 registration | 18:00 | 18:50 | 50 min | approved | PMS
Break | Morning Break | 11:15 | 11:30 | 15 min | approved | Manual
Break | Lunch | 14:15 | 14:45 | 30 min | approved | Manual
Break | Evening Break | 17:30 | 17:45 | 15 min | approved | Manual
📅 Tuesday, July 7
Project | Task | Start | End | Duration | Status | Source
TDS FILING FY2026-27 | Pan & bills verification for Jun 2026 CTI | 09:50 | 11:15 | 85 min | approved | PMS
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses | 11:30 | 14:00 | 150 min | approved | PMS
IT Filing CTI 2025-26 | Coordination with IT filing CTI | 14:00 | 17:15 | 195 min | approved | PMS
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 | 17:30 | 18:15 | 45 min | approved | PMS
Monthly Budget Forecasting 2026-27 | Excel Workings & confirmation of Budget July 2026 | 18:15 | 18:50 | 35 min | approved | PMS
Break | Morning Break | 11:15 | 11:30 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:15 | 17:30 | 15 min | approved | Manual
📅 Wednesday, July 8
Project | Task | Start | End | Duration | Status | Source
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses | 09:45 | 11:15 | 90 min | approved | PMS
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing | 11:30 | 14:00 | 150 min | approved | PMS
IT Filing CTI 2025-26 | Coordination with IT filing CTI | 14:30 | 17:15 | 165 min | approved | PMS
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 | 17:30 | 18:15 | 45 min | approved | PMS
Monthly Budget Forecasting 2026-27 | Budget Analysis for the month of July 2026 | 18:15 | 18:50 | 35 min | approved | PMS
Break | Morning Break | 11:00 | 11:15 | 15 min | approved | Manual
Break | Lunch | 14:00 | 14:30 | 30 min | approved | Manual
Break | Evening Break | 17:15 | 17:30 | 15 min | approved | Manual
📅 Thursday, July 9
Project | Task | Start | End | Duration | Status | Source
Oracle Fusion | Registration Proceeding of HTL India - Hexaware | — | — | — | pending | Manual
Monthly Budget Forecasting 2026-27 | Excel Workings & confirmation of Budget July 2026 | 09:55 | 10:35 | 40 min | approved | PMS
Bike Insurance | Evaluation & Confirmation of Quote for Bike Insurance | 10:35 | 11:15 | 40 min | approved | PMS
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing | 11:15 | 14:15 | 180 min | approved | PMS
Vendor Bills Reconciliation 2026-27 | Reconciliation of vendor bills against Zoho books Apr-May 2026 | 14:45 | 15:30 | 45 min | approved | PMS
Bank Statement reconciliation CTI ICICI 2025-26 | Updating Entries in Zoho Books CTI ICICI 2025-26 | 15:30 | 16:30 | 60 min | approved | PMS
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses | 16:30 | 17:15 | 45 min | approved | PMS
Finance Project Report 2026-27 | Reconciliation of project wise report against Zoho Books CTI Jun 2026 | 17:30 | 18:00 | 30 min | approved | PMS
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 | 18:00 | 19:00 | 60 min | approved | PMS
Break | Morning Break | 11:15 | 11:30 | 15 min | approved | Manual
Break | Lunch | 14:15 | 14:45 | 30 min | approved | Manual
Break | Evening Break | 17:15 | 17:30 | 15 min | approved | Manual
📅 Friday, July 10
Project | Task | Start | End | Duration | Status | Source
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 | 10:00 | 11:15 | 75 min | approved | PMS
Bike Insurance | Evaluation & Confirmation of Quote for Bike Insurance | 11:30 | 12:00 | 30 min | approved | PMS
Vendor Bills Reconciliation 2026-27 | Reconciliation of vendor bills against Zoho books Apr-May 2026 | 12:00 | 13:00 | 60 min | approved | PMS
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses | 13:00 | 14:05 | 65 min | approved | PMS
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing | 14:35 | 17:15 | 160 min | approved | PMS
IT Filing CTI 2025-26 | Coordination with IT filing CTI | 17:30 | 19:00 | 90 min | approved | PMS
Break | Morning Break | 11:15 | 11:30 | 15 min | approved | Manual
Break | Lunch | 14:05 | 14:35 | 30 min | approved | Manual
Break | Evening Break | 17:15 | 17:30 | 15 min | approved | Manual