## Durga Devi
Timesheet Report — Durga Devi ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
BOQ software | Creation of new features and debugging ¦ fixing the colour change and approval errors in generate bom ¦ Fixed color display inconsistencies and approval workflow errors in Generate BOM to improve usability, workflow accuracy, and approval process reliability. | 10:00 | 12:00 | 2h 0m | manager_approved | 6 UI issues resolved, 5 approval workflow errors fixed, 8 validation scenarios completed, 4 workflow consistency improvements implemented | Resolved color display inconsistencies and approval workflow errors in the Generate BOM module, improving visual clarity, approval processing, and overall user experience. | New Features |  |  |  | 100%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ fixing the data loading and the performance issues in the task page ¦ Optimized data loading and resolved performance issues in the Task page, improving response time, rendering speed, and overall application efficiency. | 12:00 | 14:25 | 2h 25m | manager_approved | 7 performance bottlenecks resolved, 5 data loading workflows optimized, 8 validation scenarios completed, 4 response time improvements implemented | Optimized the Task page by resolving data loading delays and performance bottlenecks, improving response times, reducing rendering latency, and delivering a smoother user experience after file modularization. | Updates and features |  |  |  | 80%
Payroll Management | Updates of application and debugging ¦ creation of new attendance tracking for the each employees in the payroll page ¦ Implemented employee-wise attendance tracking in the Payroll page to improve attendance visibility, payroll accuracy, and overall payroll processing efficiency. | 14:55 | 16:00 | 1h 5m | manager_approved | 1 attendance tracking feature implemented, 5 payroll workflows enhanced, 8 validation scenarios completed, 4 data integration improvements delivered | Developed a new attendance tracking feature in the Payroll page, enabling employee-wise attendance visibility and improving payroll calculation accuracy through integrated attendance data. | Features and updates |  |  |  | 70%
Payroll Management | Updates of application and debugging ¦ Resolving the error in the missing timesheet ¦ Fixed missing timesheet errors by improving data validation and synchronization, ensuring accurate timesheet retrieval and reliable payroll processing. | 16:00 | 17:30 | 1h 30m | manager_approved | 6 timesheet validation issues resolved, 5 payroll processing workflows corrected, 8 validation scenarios completed, 4 data synchronization improvements implemented | Resolved missing timesheet errors by correcting data validation and synchronization logic, ensuring accurate timesheet retrieval and reliable payroll processing. | Features and updates |  |  |  | 90%
Payroll Management | Updates of application and debugging ¦ Integration of punch times with the payroll calculation ¦ Integrated punch-in and punch-out times with payroll calculations to automate working hour computation and improve payroll accuracy and efficiency. | 17:45 | 19:45 | 2h 0m | manager_approved | 1 payroll integration feature implemented, 5 payroll calculation workflows enhanced, 8 validation scenarios completed, 4 attendance synchronization improvements delivered | Integrated employee punch-in and punch-out times with the payroll calculation process, ensuring accurate working hour computation and improving payroll accuracy through automated attendance-based calculations. | Features and updates |  |  |  | 80%
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Payroll Management | Debugging and updates ¦ Integration of the biometric in the payroll calculation ¦ Integrated biometric attendance with payroll calculations to automate attendance processing, improve working hour accuracy, and ensure reliable payroll computation. | 10:00 | 11:45 | 1h 45m | manager_approved | 1 biometric integration completed, 5 payroll calculation workflows enhanced, 8 validation scenarios completed, 4 attendance synchronization improvements implemented | Integrated biometric attendance data with the payroll calculation process, enabling automatic attendance retrieval, accurate working hour calculations, and improved payroll processing reliability. | Features and updates |  |  |  | 90%
Payroll Management | Debugging and updates ¦ creation of new analysis option and api integration ¦ Created a new payroll analysis feature and integrated backend APIs to improve reporting, data visibility, and payroll analysis capabilities. | 11:45 | 13:00 | 1h 15m | manager_approved | 1 analysis feature implemented, 6 API endpoints integrated, 8 validation scenarios completed, 4 reporting workflows enhanced | Developed a new analysis module and integrated the required APIs to provide payroll insights, improve data visualization, and enable accurate reporting through reliable backend communication. | Features and updates |  |  |  | 100%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ Error handling due the data mismatch occured in spiliting the files ¦ Resolved data mismatch issues during file splitting by implementing error handling, improving data consistency, module stability, and overall application performance. | 13:00 | 14:20 | 1h 20m | manager_approved | 6 data mismatch issues resolved, 5 error-handling routines implemented, 8 validation scenarios completed, 4 module integration issues corrected | Implemented robust error handling to resolve data mismatch issues encountered during the file-splitting process, ensuring data consistency, stable module interactions, and improved application performance. | Updates and features |  |  |  | 70%
Payroll Management | Debugging and updates ¦ fixing the leave deduction calculation errors in the payroll ¦ Fixed leave deduction calculation errors in payroll by improving calculation logic, leave validation, and payroll accuracy. | 14:50 | 16:00 | 1h 10m | manager_approved | 6 payroll calculation issues resolved, 5 leave deduction rules corrected, 8 payroll validation scenarios completed, 4 calculation workflows optimized | Resolved leave deduction calculation errors by correcting payroll logic, validating leave records, and ensuring accurate salary deductions based on approved leave policies. | Features and updates |  |  |  | 80%
Payroll Management | Debugging and updates ¦ fixing the mismatch of data between the punch in and out timings ¦ Fixed punch-in and punch-out data mismatch issues to ensure accurate attendance records, working hour calculations, and reliable payroll processing. | 16:00 | 17:30 | 1h 30m | manager_approved | 4 attendance synchronization issues resolved, 5 payroll validation rules corrected, 8 attendance scenarios verified, 4 data consistency improvements implemented | Resolved data mismatches between employee punch-in and punch-out records by improving attendance validation, synchronization logic, and payroll integration, ensuring accurate working hour calculations. | Features and updates |  |  |  | 100%
Payroll Management | Debugging and updates ¦ added new sandwich deduction and punch timings deduction in payroll calculation ¦ Implemented sandwich leave and punch timing deductions in payroll calculations to automate policy-based salary deductions and improve payroll accuracy. | 17:30 | 19:00 | 1h 30m | manager_approved | 2 new payroll deduction rules implemented, 6 payroll calculation workflows enhanced, 8 validation scenarios completed, 4 policy-based deduction checks integrated | Implemented Sandwich Leave deduction and Punch Timing deduction rules in the payroll calculation module, ensuring payroll processing complies with attendance and leave policies while improving calculation accuracy. | Features and updates |  |  |  | 100%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ Error handling due the data mismatch occured in spiliting the files ¦ Resolved data mismatch issues during file splitting by implementing robust error handling, improving module stability, data consistency, and overall application performance. | 09:30 | 11:00 | 1h 30m | manager_approved | 6 data mismatch issues resolved, 5 error-handling mechanisms implemented, 8 validation scenarios completed, 4 module integration issues corrected | Implemented comprehensive error handling to resolve data mismatch issues encountered during the file-splitting process, ensuring accurate data flow, stable module integration, and improved application performance after code modularization. | Updates and features |  |  |  | 70%
Timeguard-Monitoring system | Creation of Mac Desktop Agent ¦ fixing the data capturing and storing issues and activity tracking issues ¦ Fixed data capture, storage, and activity tracking issues in the Mac Desktop Agent to improve monitoring accuracy, data reliability, and overall system performance. | 11:00 | 12:45 | 1h 45m | manager_approved | 3 data capture issues resolved, 5 activity tracking workflows optimized, 8 validation scenarios completed, 4 data storage improvements implemented | Resolved issues related to data capture, data storage, and activity tracking in the Mac Desktop Agent, improving monitoring accuracy, data reliability, and overall agent performance. | Architecture building |  |  |  | 60%
Payroll Management | Debugging and updates ¦ fixing the calculation errors in the admin panel and fixing lint errors | 12:45 | 14:15 | 1h 30m | manager_approved | 2 calculation issues resolved, 20+ lint errors fixed, 1 validation scenarios completed, 2 admin workflows optimized | Resolved payroll calculation errors in the Admin Panel by correcting business logic and validation rules, while fixing lint issues to improve code quality, maintainability, and application stability. | Features and updates |  |  |  | 80%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ correcting the date format and creation od cancelled status for projects and keysteps ¦ Standardized the application date format and implemented a Cancelled status for Projects and Key Steps to improve consistency, status tracking, and project lifecycle management. | 14:45 | 16:00 | 1h 15m | manager_approved | 2 core enhancements implemented, 4 date fields standardized to DD/MM/YYYY format, 2 new status workflows (Projects & Key Steps) introduced, 9 functional test cases verified | Standardized date formatting across the application and introduced a Cancelled status for Projects and Key Steps, ensuring consistent data presentation and improved project lifecycle management. | Updates and features |  |  |  | 100%
Payroll Management | Debugging and updates ¦ Project Discussion-Regarding the Payroll with Sam sir. ¦ Participated in a project discussion with Sam Sir to review payroll enhancements, resolve implementation queries, and finalize priorities for upcoming feature development. | 16:00 | 17:00 | 1h 0m | manager_approved | 1 project review meeting conducted, 9 payroll enhancement requirements discussed, 3 implementation tasks identified | Conducted a detailed discussion with Sam Sir to review the Payroll Management system, evaluate ongoing development, prioritize feature enhancements, and finalize the implementation approach for upcoming releases. | Features and updates |  |  |  | 100%
Payroll Management | Debugging and updates ¦ fixing the attendance logs api errors in the daily analysis page ¦ Fixed attendance log API errors in the Daily Analysis page to improve data accuracy, API reliability, and overall payroll analytics performance. | 17:00 | 17:30 | 0h 30m | manager_approved | 4 attendance log APIs corrected, 2 API response issues resolved, 7 data validation checks completed, 3 dashboard data retrieval workflows optimized | Resolved attendance log API issues in the Daily Analysis page by correcting endpoint integration, improving data retrieval, and ensuring accurate attendance information was displayed. | Features and updates |  |  |  | 100%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ In Task, Assignee's name list is not visible based on department There is no scroll for projects in Task filter and fixing lint errors ¦ Fixed department-based assignee filtering, added scrolling to the Project filter, and resolved lint issues to improve usability, code quality, and application stability. | 17:45 | 19:00 | 1h 15m | manager_approved | 3 functional issues resolved, 2 UI components enhanced | Resolved the department-based assignee list issue in the Task module, added scrolling support for the Project filter, and eliminated lint errors to improve usability, code quality, and overall application stability. | Updates and features |  |  |  | 100%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ fixing the data loading and the performance issues in the task page ¦ Optimized data loading and resolved Task page performance issues by improving rendering efficiency, reducing unnecessary processing, and enhancing overall application responsiveness. | 10:00 | 11:30 | 1h 30m | manager_approved | 5 data loading bottlenecks eliminated, 3 task page components optimized, 14 database/API calls streamlined, 9 performance validation scenarios completed | Optimized the Task page by improving data loading mechanisms, reducing unnecessary processing, and enhancing rendering performance, resulting in a faster and more responsive user experience. | Updates and features |  |  |  | 100%
BOQ software | Creation of new features and debugging ¦ Project Discussion With sam sir. ¦ Participated in a project discussion with Sam Sir to review feature enhancements, resolve implementation queries, and finalize priorities for upcoming BOQ development. | 11:30 | 12:45 | 1h 15m | manager_approved | 1 technical review meeting conducted, 11 feature enhancement requests discussed, 6 implementation tasks identified | Conducted a comprehensive discussion with Sam Sir to review the BOQ application, evaluate ongoing development, prioritize new feature requests, and finalize the implementation strategy for upcoming enhancements. | New Features |  |  |  | 100%
Payroll Management | Refinement of payroll page with updates ¦ payroll updating features with the OD leave detection ¦ Integrated OD leave detection into payroll processing to ensure accurate attendance validation and salary calculation based on approved On Duty records. | 12:45 | 14:15 | 1h 30m | manager_approved | 1 OD leave detection feature implemented, 6 payroll calculation rules updated, 9 attendance validation scenarios verified, 4 payroll processing workflows refined | Enhanced the payroll module by integrating OD (On Duty) leave detection, ensuring OD records are accurately considered during payroll processing and attendance-based salary calculations. | Features and updates |  |  |  | 81%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ creation of new calendar option and ui refinement ¦ Developed a new calendar feature and refined the user interface to improve task scheduling, planning visibility, and the overall user experience. | 14:45 | 16:00 | 1h 15m | manager_approved | 1 new calendar module introduced, 7 UI components refined, 5 calendar interactions implemented, 12 functional and usability test cases validated | Developed a new calendar feature and refined the user interface to improve task scheduling, event visualization, and overall usability, providing a more intuitive planning experience. | Updates and features |  |  |  | 90%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ addition of new event creation fields and added export option ¦ Added new event creation fields and an export option to improve event management, data capture, and reporting functionality within the application. | 16:00 | 17:15 | 1h 15m | manager_approved | 6 new event fields implemented, 1 export feature added, 5 event management workflows enhanced | Enhanced the event management module by introducing additional event creation fields and implementing an export option, improving event planning, data capture, and reporting capabilities. | Updates and features |  |  |  | 80%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ Schema creation for storing the calendar events and api integartion ¦ Designed the calendar event database schema and integrated backend APIs to support reliable event storage, management, and synchronization across the application. | 17:30 | 19:00 | 1h 30m | manager_approved | 1 calendar event schema designed, 3 database tables and relationships configured, 5 API endpoints integrated, 11 backend validation scenarios completed | Designed and implemented the database schema for calendar events and integrated the required APIs, enabling reliable event creation, retrieval, updates, and synchronization across the application. | Updates and features |  |  |  | 100%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Project management software | PMS spliting the files to ensure the data performances and fixing | 10:00 | 12:00 | 02:00 | draft | [6 empty] | 0%
Payroll Management | Refinement of payroll page with updates | 12:00 | 14:00 | 02:00 | draft | [6 empty] | 0%
Site Management app | Database connection and Development | 14:00 | 16:00 | 02:00 | draft | [6 empty] | 0%
BOQ software | Creation of new features and debugging | 16:00 | 17:00 | 01:00 | draft | [6 empty] | 0%
Timeguard-Monitoring system | Creation of Mac Desktop Agent | 17:15 | 19:00 | 01:45 | draft | [6 empty] | 0%

## Mohanraj C
Timesheet Report — Mohanraj C ¦ July 6–10, 2026
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Vendor Bills Reconciliation 2026-27 | Reconciliation of vendor bills against Zoho books Apr-May 2026 ¦ ¦ Performed vendor account reconciliation by matching vendor bills with Zoho Books records for April–May 2026, verifying ledger balances, resolving discrepancies, and ensuring accurate financial reporting. | 10:00 | 11:00 | 1h 0m | manager_approved | 9 vendor accounts reconciled and verified | Successfully reconciled vendor bills against Zoho Books for April–May 2026, verified ledger balances, and identified discrepancies for correction. | Vendor Account reconciliation |  |  |  | 95%
TDS Reconciliation FY 2025-26 – SGK Auditors | TDS Reconciliation & Verification – FY 2025-26 with SGK Auditors ¦ ¦ Performed TDS reconciliation and verification for FY 2025-26 by matching ledger balances with supporting records, identifying discrepancies, and coordinating with SGK Auditors for resolution and audit completion. | 11:15 | 14:00 | 2h 45m | manager_approved | 15 TDS transactions reconciled and verified | Successfully reconciled TDS transactions for FY 2025-26, verified ledger balances with supporting documents, and coordinated with SGK Auditors to resolve discrepancies. | TDS Reconciliation |  |  |  | 95%
TDS FILING FY2026-27 | Form 13 Application TDS - CTI ¦ ¦ Prepared and processed the Form 13 application for CTI by compiling the required documents, verifying financial details, and coordinating the submission process to facilitate TDS-related compliance requirements. | 14:30 | 17:00 | 2h 30m | manager_approved | 1 Form application prepared and processed | Successfully prepared the Form 13 application, verified supporting documents, and coordinated the submission process for CTI. |  |  |  |  | 90%
Contractors' All Risks (CAR) Insurance | Contractors' All Risks (CAR) Insurance – Proposal Preparation & Policy Processing ¦ ¦ Prepared and submitted the Contractors' All Risks (CAR) insurance proposal, coordinated with the insurer for documentation requirements, verified policy details, and supported the policy issuance process to ensure project insurance compliance. | 17:15 | 19:00 | 1h 45m | manager_approved | 1 CAR insurance proposal prepared and processed | Successfully prepared the CAR insurance proposal, coordinated the required documentation, and facilitated the policy processing for project insurance compliance. | Insurance Compliance |  |  |  | 95%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
GST Filing 2026-27 | GSTR verification, reconciliation & filing of Jun 2026 ¦ ¦ Performed analysis and working for GSTR filing for June 2026 by verifying GST transactions, reconciling records with Zoho Books, resolving discrepancies, and preparing the data for accurate GST filing. | 10:00 | 11:00 | 1h 0m | pending | 2 GST returns analyzed and reconciled | Successfully completed the analysis and workings for GSTR filing for June 2026, reconciled GST data with accounting records, and ensured filing readiness. | GST Workings |  |  |  | 90%
Bank Statement reconciliation CTI ICICI 2025-26 | ICICI Bank Statement Analysis and Excel Working - CTI 2026 ¦ Excel Working and Analysis - April-26 to Jun-26 ¦ Analyzed ICICI Bank statement transactions and compared them with Zoho Books records to identify discrepancies, prepare Excel workings, and update the required corrections for accurate bank reconciliation for FY 2025-26. | 11:15 | 14:00 | 2h 45m | pending | 23 bank transactions analyzed and verified | Successfully analyzed ICICI Bank transactions, compared them with Zoho Books records, identified discrepancies, and updated the required corrections for accurate reconciliation. |  |  |  |  | 90%
Finance Project Report 2026-27 | Reconciliation of project wise report against Zoho Books CTI Jun 2026 ¦ ¦ Performed reconciliation of project-wise reports against Zoho Books records for CTI - June 2026 by verifying project revenue, expenses, estimates, purchase orders, and invoices to ensure accurate financial reporting and project tracking. | 14:30 | 17:00 | 2h 30m | pending | 15 project records reconciled and verified | Successfully reconciled project-wise financial reports with Zoho Books records for CTI - June 2026 and ensured the accuracy of project revenue, expenses, and billing information. | Reconciliation |  |  |  | 90%
Vendor Bills Reconciliation 2026-27 | Reconciliation of vendor bills against Zoho books Apr-May 2026 ¦ ¦ Performed reconciliation of vendor bills against Zoho Books for April–May 2026 by verifying invoice details, matching vendor records, resolving discrepancies, and ensuring accurate accounting records. | 17:15 | 19:00 | 1h 45m | pending | 7 vendor bills reconciled and verified | Successfully reconciled vendor bills with Zoho Books records for April–May 2026, identified discrepancies, and ensured accurate vendor accounting balances. | Reconciling vendor bills |  |  |  | 80%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Sales invoice Raising 2026-27 | Hexaware Sales Invoice Creation ¦ ¦ Prepared estimates and created sales invoices for Hexaware projects by verifying project details, purchase orders, and billing requirements, ensuring accurate and timely invoice generation. | 10:00 | 11:00 | 1h 0m | manager_approved | 1 sales invoices created and verified | Successfully prepared estimates and created sales invoices for Hexaware projects, ensuring accuracy in billing details and compliance with client requirements. | Create Estimate |  |  |  | 95%
ICICI, HDFC & KVB Bank Statement Category Working | Bank Statement Categorization & Verification – ICICI, HDFC & KVB ¦ ¦ Performed categorization and verification of bank transactions from ICICI, HDFC, and KVB statements by classifying entries, validating transaction details, and supporting reconciliation and financial reporting activities. | 11:15 | 14:00 | 2h 45m | manager_approved | 35 bank transactions categorized and verified | Successfully analyzed and categorized transactions from ICICI, HDFC, and KVB bank statements, ensuring accurate classification and reconciliation for financial reporting. | Bank Statement Analysis |  |  |  | 85%
OD Registration Coordination – HDFC & Finance Limited | OD Registration Coordination, Documentation & Follow-up – HDFC & Finance Limited ¦ ¦ Coordinated the OD registration process with HDFC Bank and Finance Limited by reviewing documentation requirements, verifying submitted records, and following up with stakeholders to facilitate timely approval and completion of the registration process. | 14:30 | 15:30 | 1h 0m | manager_approved | 2 registration documents reviewed and coordinated | Successfully coordinated with HDFC Bank and Finance Limited for OD registration, verified documentation requirements, and followed up on the application process to ensure timely completion. | Bank Coordination |  |  |  | 90%
Project name Creation in Zoho Books - CTI & KPL | Zoho Books Project Setup & Creation – CTI & KPL ¦ ¦ Created and configured project names in Zoho Books for CTI and KPL by updating customer details, project information, and financial tracking parameters to support accurate project accounting and reporting. | 15:30 | 16:30 | 1h 0m | manager_approved | 5 project names created and configured | Successfully created and configured project names in Zoho Books for CTI and KPL, ensuring proper project mapping and accurate financial tracking. | System Configuration |  |  |  | 90%
GST Filing 2026-27 | Analysis & working of GSTR filing Jun 2026 ¦ ¦ Performed analysis and working for GSTR filing for June 2026 by verifying GST transactions, reconciling records with Zoho Books, resolving discrepancies, and preparing the data for accurate GST filing. | 16:30 | 17:00 | 0h 30m | manager_approved | 2 GST returns analyzed and reconciled | Successfully completed the analysis and workings for GSTR filing for June 2026, reconciled GST data with accounting records, and ensured filing readiness. | Verification, Reconciliation & Filing |  |  |  | 95%
BOQ working - CTI and KPL | BOQ Preparation, Review & Cost Estimation – CTI & KPL ¦ ¦ Prepared, reviewed, and verified BOQs for CTI and KPL projects, including quantity take-off, cost estimation, and validation of material and labour requirements to support project execution and quotation preparation. | 17:15 | 19:00 | 1h 45m | manager_approved | 2 BOQs prepared and reviewed | Successfully prepared and reviewed BOQs for CTI and KPL projects, verified quantities, and completed cost estimations to support project budgeting and quotation preparation. | BOQ Preparation |  |  |  | 95%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
ICICI, HDFC & KVB Bank Statement Category Working | Bank Statement Categorization & Verification – ICICI, HDFC & KVB | 10:00 | 11:00 | 01:00 | draft | [6 empty] | 0%
MD Cabin Setup | CDW - Quotation revision | 11:15 | 14:00 | 02:45 | draft | [6 empty] | 0%
Vendor Payment | Verification of Vendor Payment Apr-Jul 2026 | 14:30 | 17:00 | 02:30 | draft | [6 empty] | 0%
Sales invoice Raising 2026-27 | Verification of SL interior Measurement sheet | 17:15 | 19:00 | 01:45 | draft | [6 empty] | 0%

## Pushpa Prithviraj
Timesheet Report — Pushpa Prithviraj ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | Timesheet Review & Validation ¦ | 10:00 | 11:30 | 1h 30m | pending | Timesheet validated for all employees | Successfully evaluated all employees timesheet | Timesheet Validation |  |  |  | 40%
HR Operations | Meeting with sam sir ¦ ¦ Participated in a meeting with Sivakumar Sir to discuss work allotments, task distribution, project priorities, and resource allocation. Reviewed current assignments, clarified responsibilities, and aligned on timelines to ensure efficient execution of ongoing activities. | 11:45 | 12:45 | 1h 0m | pending | Attended 1 work allocation meeting | Gained clarity on task ownership and priorities, ensured effective work distribution, improved coordination among team members, and supported the timely execution of assigned responsibilities. Problems & Issues: Changes in work priorities, reso | Analysing |  |  |  | 30%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles ¦ ¦ Managed the recruitment process for the Purchase Assistant role by sourcing candidates, screening resumes, conducting initial interviews. | 12:45 | 14:20 | 1h 35m | pending | Sourced and screened 12 candidate profiles | Successfully evaluated 12 candidates for role suitability | Sourcing |  |  |  | 40%
HR Operations | Meeting with sam sir ¦ ¦ Participated in a meeting with Sam Sir to review payroll processing, salary calculations, attendance records, statutory deductions, reimbursements, and payroll-related queries. | 14:50 | 15:50 | 1h 0m | pending | Attended 1 payroll review meeting | Verified payroll data, resolved payroll-related queries, ensured the accuracy of salary calculations, and supported the timely completion of payroll processing. |  |  |  |  | 30%
Site Engineer Hiring Initiative -100 | Sourcing profiles through job portals. ¦ ¦ Managed the end-to-end recruitment process for the Site Engineer position, including candidate sourcing, resume screening, interview coordination, candidate evaluation. | 15:50 | 16:50 | 1h 0m | pending | Sourced and screened 8 candidate profiles | Successfully shortlisted qualified candidates, streamlined the recruitment process, and supported the timely hiring of a suitable Site Engineer. | Sourcing |  |  |  | 40%
HR Operations | HR Position Interview ¦ ¦ Conducted a meeting with an HR candidate to discuss the job role, responsibilities, organisational expectations, compensation, notice period. | 16:50 | 18:00 | 1h 10m | pending | Conducted 1 meeting with an HR candidate | Clarified the role and expectations, assessed the candidate's overall fit for the position, and supported the recruitment process by progressing the candidate to the next stage. |  |  |  |  | 40%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution ¦ | 18:15 | 19:00 | 0h 45m | pending | Sourced and screened 7 candidate profiles | Successfully evaluated 7 candidates for role suitability | Sourcing |  |  |  | 40%
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | LMS Update & Monitoring ¦ | 10:00 | 11:00 | 1h 0m | pending | Availed 1 hour of approved permission. | Maintained clear communication with the reporting manager and ensured work continuity despite the short absence. | Biometric System |  |  |  | 30%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution ¦ ¦ Conducted an interview with a Site Engineer candidate to assess technical knowledge, site execution experience, project coordination skills, construction practices, problem-solving abilities, communication skills, and overall suitability for the role. | 11:00 | 12:30 | 1h 30m | pending | Interviewed 1 Site Engineer candidate | Successfully evaluated the candidate's technical competencies and project experience, identified strengths relevant to the role, and supported the recruitment process by recommending the candidate for the next stage. | Scheduling the interview with candidate . |  |  |  | 30%
Pay sheet | Alphaori Attendance Sheet Preparation ¦ ¦ Visited the Alpha Ori office to verify employee attendance records and facilitate the signing of the agreement. Coordinated with the client, ensured the required documentation was completed | 12:30 | 13:45 | 1h 15m | pending | Completed 1 client office visit | Successfully verified attendance records, facilitated the agreement signing process, ensured timely completion of documentation, and maintained effective client coordination. |  |  |  |  | 50%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles ¦ ¦ Sourced and screened candidates for the Purchase Assistant position through job portals, referrals, professional networks, and candidate databases. | 13:45 | 14:20 | 0h 35m | pending | Sourced and screened 7 candidate profiles | Successfully evaluated 7 candidates for role suitability | Sourcing |  |  |  | 40%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution ¦ ¦ Sourced and screened candidates for the Quantity Surveyor (QS) position through job portals, referrals, professional networks. | 14:50 | 17:00 | 2h 10m | pending | Sourced and screened 12 candidate profiles | Successfully evaluated 12 candidates for role suitability | Sourcing |  |  |  | 40%
Pay sheet | Timesheet Review & Validation ¦ | 17:15 | 19:00 | 1h 45m | pending | Timesheet validated for all employees | Successfully evaluated all employees timesheet | Timesheet Validation |  |  |  | 39%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution ¦ ¦ Conducted an interview with a Quantity Surveyor (QS) candidate to assess expertise in quantity estimation, BOQ preparation, billing, cost control, quantity take-off, project coordination, communication skills, and overall suitability for the role. | 10:00 | 11:30 | 1h 30m | pending | Interviewed 1 QS candidate | Successfully evaluated the candidate's technical competencies and relevant experience, identified strengths aligned with the role, and supported the recruitment process by recommending suitable candidates for the next stage. | Scheduling the interview |  |  |  | 30%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution ¦ ¦ Conducted an interview with a Site Engineer candidate to evaluate technical knowledge, site execution experience, project coordination skills, construction practices, safety awareness, communication skills, and overall suitability for the role. | 11:30 | 12:30 | 1h 0m | pending | Interviewed 1 Site Engineer candidate | Successfully assessed the candidate's technical competencies and project experience, identified strengths relevant to the role, and supported the recruitment process by recommending the candidate for the next stage. | Scheduling the interview with candidate . |  |  |  | 30%
HR Operations | HR Position Interview ¦ ¦ Conducted an interview with an HR candidate to assess recruitment expertise, HR operations knowledge, employee relations experience, communication skills, problem-solving abilities, and overall suitability for the role. | 12:30 | 13:00 | 0h 30m | pending | Interviewed 1 HR candidate | Successfully evaluated the candidate's qualifications, communication skills, and HR competencies, identified strengths relevant to the role, and supported the recruitment process by recommending suitable candidates for the next stage. | Analysing |  |  |  | 40%
Meet up with clients | Coordinated with Maya (Manager) ¦ | 13:00 | 13:30 | 0h 30m | pending | 1 call with maya manager |  | Attend the client meeting and discuss requirements/updates. |  |  |  | 40%
HR Operations | HR Position Interview ¦ ¦ Participated in a discussion with Sam Sir to review the HR candidate interview, evaluate the candidate's performance, discuss recruitment suitability, compensation expectations, and determine the next steps in the hiring process. | 13:30 | 14:50 | 1h 20m | pending | Attended 1 candidate review meeting | Collaboratively evaluated the candidate's strengths and areas for improvement, aligned on the hiring decision, and supported the recruitment process through effective discussion and feedback. | Analysing |  |  |  | 40%
HR Operations | Meeting with sam sir ¦ ¦ Discussion with sam sir regarding payroll | 15:20 | 17:00 | 1h 40m | pending | 1 payroll discussion | [5 empty] | 30%
HR Operations | Offer Letter Preparation & Coordination ¦ ¦ Offer released for site engineer and qs candidate | 17:15 | 19:00 | 1h 45m | pending | 2 offer letter prepared | [5 empty] | 40%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
HR Operations | Offer Letter Preparation & Coordination ¦ ¦ Coordinated and completed the onboarding process for the Site Engineer and Quantity Surveyor (QS) by collecting and verifying joining documents, completing employment formalities. | 10:00 | 11:30 | 1h 30m | pending | Successfully completed the onboarding process for 2 employees | Ensured seamless onboarding, completed all required documentation on time, coordinated with internal departments for access and induction, and enabled both employees to begin their roles without delays. |  |  |  |  | 40%
Hiring Interns | Screening Candidates ¦ ¦ Conducted interviews with candidates for the Quantity Surveyor (QS) and Purchase positions to assess their technical knowledge, relevant work experience, communication skills, problem-solving abilities. | 11:45 | 13:00 | 1h 15m | pending | Interviewed 2 candidates | Successfully evaluated the candidates' competencies, identified suitable profiles for the respective roles, and supported the recruitment process by recommending qualified candidates for the next stage. | Candidate Selection Process |  |  |  | 40%
Pay sheet | Timesheet Review & Validation ¦ | 13:00 | 14:20 | 1h 20m | pending | Timesheet validated for all employees | Successfully evaluated all employees timesheet | Timesheet Validation |  |  |  | 40%
HR Operations | Meeting with sam sir ¦ ¦ Participated in a meeting with Sam Sir to discuss ongoing hiring requirements, candidate status, recruitment priorities, interview feedback, open positions, and strategies for timely closure of vacancies. | 14:50 | 15:50 | 1h 0m | pending | Attended 1 hiring review meeting | Aligned on recruitment priorities, clarified hiring decisions, reviewed candidate progress, and supported the timely execution of recruitment activities. | Gathered Information |  |  |  | 40%
Pay sheet | Verified the OT details before sending them to Sam Sir ¦ ¦ Prepared the overtime (OT) details for Umar and Mathesh by verifying attendance records, overtime hours, shift details, and supporting data. Ensured the OT calculations were accurate before sharing them for payroll processing. | 15:50 | 16:50 | 1h 0m | pending | Prepared and verified OT details for 2 employees | Ensured accurate overtime calculations, maintained proper payroll documentation, and submitted the OT details within the required timeline for payroll processing. | Timesheet Validation |  |  |  | 30%
HR Operations | HR Position Interview ¦ | 16:50 | 17:30 | 0h 40m | pending | Interview with hr candidate -1 |  | Analysing |  |  |  | 40%
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring ¦ Analyze client requirements (language, experience, targets) | 17:45 | 19:00 | 1h 15m | pending | Sourced and screened 7 candidate profiles | Successfully evaluated 7 candidates for role suitability | Schedule interviews with client company |  |  |  | 30%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | Timesheet Review & Validation ¦ | 10:00 | 11:30 | 1h 30m | draft | Timesheet validated for all employees | Successfully evaluated all employees timesheet |  |  |  |  | 30%
HR Operations | Vendor Follow-up for Housekeeping Services | 17:15 | 17:45 | 00:30 | draft | [6 empty] | 0%
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 17:45 | 18:15 | 00:30 | draft | [6 empty] | 0%
Meet up with clients | Client Relationship Management | 18:15 | 18:45 | 00:30 | draft | [6 empty] | 0%
Meet up with clients | Coordinated the ISON client meet-up to ensure smooth communication and successful execution . | 18:45 | 19:15 | 00:30 | draft | [6 empty] | 0%
Meet up with clients | Coordinated with Maya (Manager) | 19:15 | 19:45 | 00:30 | draft | [6 empty] | 0%
HR Operations | DA and Professional Tax Data Collection | 19:45 | 20:15 | 00:30 | draft | [6 empty] | 0%
Pay sheet | Edited the salary slips and sent them to all employees | 20:15 | 20:45 | 00:30 | draft | [6 empty] | 0%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 20:45 | 21:15 | 00:30 | draft | [6 empty] | 0%
HR Operations | HR Position Interview | 21:15 | 21:45 | 00:30 | draft | [6 empty] | 0%
HR Operations | Meeting with sam sir | 21:45 | 22:15 | 00:30 | draft | [6 empty] | 0%
Workforce Productivity Tracking Initiative | Monitor and analyze employee attendance and productivity data to improve operational efficiency. | 22:15 | 22:45 | 00:30 | draft | [6 empty] | 0%
Talent acquisition | Procurement Role Candidate Identification | 22:45 | 23:15 | 00:30 | draft | [6 empty] | 0%
Talent acquisition | Production Operator Candidate Sourcing | 23:15 | 23:45 | 00:30 | draft | [6 empty] | 0%
Pay sheet | Project entry and configuration in pms . | 23:45 | 23:59 | 00:14 | draft | [6 empty] | 0%
Hiring Interns | Screening Candidates | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Hiring Interns | Sourcing Candidates | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%

## Rebecasuji
Timesheet Report — Rebecasuji ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ Error handling due the data mismatch occured in spiliting the files ¦ Worked on resolving data mismatch and integration errors introduced during PMS task file splitting by fixing data mappings | 10:00 | 11:30 | 1h 30m | pending | Resolved 6 data mismatch errors, fixed 5 split-module integration issues, and tested 10 PMS task data workflows. | Successfully handled data mismatch errors caused during the PMS file-splitting process, improving module synchronization, data consistency, task page stability, and overall application performance. | Provide New Features |  |  |  | 70%
BOQ software | Creation of new features and debugging ¦ fixing the excel and pdf values errors and submission errors in generate bom ¦ Worked on fixing Excel and PDF value errors and Generate BOM submission issues by improving data mapping, calculation validation, export processing, and submission workflows to ensure accurate and reliable BOM generation. | 11:45 | 14:00 | 2h 15m | pending | Resolved 6 Excel and PDF value errors, fixed 4 Generate BOM submission issues, and tested 10 export and submission workflows. | Successfully fixed Excel and PDF value inconsistencies and resolved submission errors in the Generate BOM module, improving data accuracy, export reliability, calculation consistency, and BOM submission stability. | Issues Resolution |  |  |  | 80%
Payroll Management | Debugging and updates ¦ Integration of the biometric in the payroll calculation ¦ Worked on integrating biometric attendance data into payroll calculations by validating employee punch-in and punch-out records, synchronizing attendance data, and updating payroll calculation logic to ensure accurate and reliable salary processing | 14:30 | 16:00 | 1h 30m | pending | Integrated 1 biometric attendance workflow, updated 5 payroll calculation processes, and tested 10 attendance and salary calculation scenarios. | Successfully integrated biometric attendance data into the payroll calculation process, improving employee working-hour validation, attendance accuracy, and automated salary calculation reliability | Features and updates |  |  |  | 70%
Sketch a plan -Mobile appliation | Debugging and Updates ¦ Refinement of the alingments and colour in the creation and plans page | 16:00 | 18:00 | 2h 0m | pending | Refined 6 UI alignment components, updated 5 color elements, and tested 8 Creation and Plans page layout scenarios. | Successfully refined the UI alignments and color schemes across the Creation and Plans pages, improving visual consistency, readability, navigation clarity, and overall mobile user experience. | Designing and implementation |  |  |  | 60%
Human Resource Management System | Requirements Analysis & System Architecture ¦ deployment in the hostinger server by installing required packages and fixed the lint errors ¦ Optimize server configuration, improve dependency management, enhance code quality validation, and strengthen the deployment workflow. | 18:00 | 19:00 | 1h 0m | pending | Project * Human Resource Management System Human Resource Management System Key Step Project Planning & System Setup Project Planning & System Setup Task * Add Deviation Requirements Analysis & System Architecture PLANNED Requirements Analysis & System ArchitecturePLANNED Sub Task * deployment in the hostinger server by installing required packages and fixed the lint errors | Successfully deployed the Human Resource Management System on the Hostinger server by configuring the deployment environment | Project Planning & System Setup |  |  |  | 80%
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ fixing the data loading and the performance issues in the task page | 10:20 | 11:20 | 1h 0m | manager_approved | Resolved 6 task page data loading issues, optimized 5 performance bottlenecks, and tested 10 task page workflows | Successfully fixed data loading and performance issues in the PMS task page, improving page response time, task data retrieval, rendering efficiency, and overall application speed. | Fix Errors |  |  |  | 70%
Payroll Management | Debugging and updates ¦ added new sandwich deduction and punch timings deduction in payroll calculation ¦ Worked on implementing sandwich deduction and punch timing-based deduction features by updating payroll calculation logic | 11:30 | 14:00 | 2h 30m | manager_approved | Implemented 2 new payroll deduction features, updated 5 payroll calculation workflows, and tested 10 salary deduction scenarios. | Successfully added sandwich deduction and punch timing-based deduction logic to payroll calculations, improving attendance validation, salary deduction accuracy, and automated payroll processing. | Features and updates |  |  |  | 50%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ fixing the data loading and the performance issues in the task page ¦ Worked on fixing data loading and performance issues in the PMS task page by optimizing API calls, data processing, component rendering, and split-file module communication to ensure faster and smoother task management workflows | 14:00 | 16:00 | 2h 0m | manager_approved | Resolved 6 task page data loading issues, optimized 5 performance bottlenecks, and tested 10 task management workflows. | Successfully fixed data loading and performance issues in the PMS task page, improving task retrieval speed, page responsiveness, rendering performance, and overall application stability. | Clear Bugs |  |  |  | 60%
Site Management app | Database connection and Development ¦ PDF updting and report making ¦ Worked on updating PDF and report generation features by refining report layouts, improving data mapping, fixing formatting and export issues, and ensuring accurate and professional site management reports. | 16:15 | 18:00 | 1h 45m | manager_approved | Updated 6 PDF report workflows, refined 5 report generation components, resolved 4 formatting issues, and tested 10 PDF export scenarios | Successfully enhanced PDF updating and report generation functionality, improving report accuracy, data presentation, document formatting, and export reliability within the Site Management application. | UI/UX designing |  |  |  | 30%
Human Resource Management System | Requirements Analysis & System Architecture ¦ deployment in the hostinger server by installing required packages and fixed the lint errors ¦ Optimize server configuration, improve dependency management, strengthen code validation, and enhance deployment performance. | 18:00 | 19:15 | 1h 15m | manager_approved | Deployed 1 HRMS application on the Hostinger server, installed 8 required packages, resolved 6 lint and build errors, and tested 10 deployment workflows. | Successfully deployed the Human Resource Management System on the Hostinger server by configuring the server environment, installing required dependencies, and resolving | Project Planning & System Setup |  |  |  | 40%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Payroll Management | Debugging and updates ¦ fixing the leave deduction calculation errors in the payroll ¦ Enhance leave validation, optimize deduction calculations, and improve payroll data synchronization and accuracy. | 10:15 | 12:15 | 2h 0m | manager_approved | Resolved 6 leave deduction calculation errors, corrected 5 payroll validation issues, and tested 10 leave and salary calculation scenarios. | Successfully fixed leave deduction calculation errors in the Payroll Management System, improving salary calculation accuracy, leave data processing, and automated payroll deduction reliability. | Features and updates |  |  |  | 40%
Payroll Management | Debugging and updates ¦ fixing the calculation errors in the admin panel and fixing lint errors ¦ Worked on resolving payroll calculation errors in the Admin Panel and fixing linting issues by improving calculation logic, data validation, code structure, and error handling to ensure accurate and stable payroll processing. | 12:30 | 14:00 | 1h 30m | manager_approved | Resolved 6 admin panel calculation errors, fixed 5 linting issues, and tested 10 payroll calculation and admin workflows. | Successfully fixed payroll calculation errors in the Admin Panel and resolved linting issues, improving calculation accuracy, code quality, system stability, and overall payroll processing reliability. | Features and updates |  |  |  | 60%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ creation of new workspace and my tasks option for the admin ¦ Enhance workspace management, improve admin-specific task filtering, optimize task visibility, and strengthen task organization workflows. | 14:30 | 16:00 | 1h 30m | manager_approved | Created 2 new admin modules, implemented 5 task filtering workflows, and tested 10 Workspace and My Tasks management scenarios. | Successfully created new Workspace and My Tasks options for the Admin Panel, improving task visibility, personalized task tracking, workspace organization, and administrative task management efficiency. | Provide New Features |  |  |  | 50%
Project management software | PMS spliting the files to ensure the data performances and fixing ¦ Error handling due the data mismatch occured in spiliting the files ¦ Enhance module synchronization, strengthen data validation, optimize shared state handling, and improve error handling across split PMS modules. | 16:00 | 19:15 | 3h 15m | manager_approved | Resolved 6 data mismatch errors, fixed 5 split-module integration issues, and tested 10 task data and API workflows. | Successfully resolved data mismatch errors caused during the PMS file-splitting process, improving data consistency, module synchronization, task page stability, and overall application performance. | Fix Errors |  |  |  | 40%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
LMS Project | Creation of new features | 10:30 | 11:40 | 01:10 | draft | [6 empty] | 0%
BOQ software | Creation of new features and debugging | 11:50 | 14:00 | 02:10 | draft | [6 empty] | 0%
Site Management app | Database connection and Development | 14:30 | 16:00 | 01:30 | draft | [6 empty] | 0%
Project management software | PMS spliting the files to ensure the data performances and fixing | 16:15 | 19:30 | 03:15 | draft | [6 empty] | 0%

## S.NAVEEN KUMAR
Timesheet Report — S.NAVEEN KUMAR ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Time88 web application | Time 88 project discussion ¦ | 10:00 | 11:15 | 1h 15m | pending | plan time 88 design and pages | discussion with sam sir and get clear ideas | Discussion |  |  |  | 90%
Time88 web application | App Suite Content Validation ¦ Reviewed app lineup, categories, icons, and content structure | 11:30 | 13:10 | 1h 40m | pending | Validated 6 application cards and content mappings | Improved product positioning and application discoverability |  |  |  |  | 58%
Time88 web application | Performance Optimization ¦ Reviewed animation, gradient rendering, and page performance | 13:10 | 14:10 | 1h 0m | pending | Evaluated 15 visual components for optimization | Improved rendering efficiency and page loading experience | integration |  |  |  | 50%
Time88 web application | Scroll-Based Card Animation ¦ Designed staggered card entrance animation workflow | 14:40 | 17:30 | 2h 50m | pending | Defined 6 animation sequences with transition parameters | Improved user engagement and interactive storytelling experience | Animation |  |  |  | 40%
Time88 web application | App Suite Gradient Enhancement ¦ Applied branded gradient backgrounds and contrast optimization | 17:45 | 19:10 | 1h 25m | pending | Updated 6 app cards with dedicated visual identities | Improved card recognition and visual differentiation | Design |  |  |  | 50%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Time88 web application | Landing page development ¦ create illustartion and animated landing page | 10:00 | 11:15 | 1h 15m | manager_approved | 1 landing page with 3 sub pages created | created 3 pages succesful in time88 | Design |  |  |  | 50%
Time88 web application | Scroll-Based Card Animation ¦ Designed staggered card entrance animation workflow | 11:30 | 14:10 | 2h 40m | manager_approved | Defined 10 animation sequences with transition parameters | Improved user engagement and interactive storytelling experience | Animation |  |  |  | 60%
Time88 web application | Performance Optimization ¦ Reviewed animation, gradient rendering, and page performance | 14:40 | 16:30 | 1h 50m | manager_approved | Evaluated 15 visual components for optimization | Improved rendering efficiency and page loading experience | integration |  |  |  | 47%
Time88 web application | Hero Section Refinement ¦ Finalized mesh gradient, wave shape, illustration placement, and sticky reveal behavior | 16:30 | 17:30 | 1h 0m | manager_approved | Refined 6 major hero components and validated 3 layout iterations | Established premium visual identity and improved first-screen engagement | Design |  | Hero transition behavior required multiple alignment adjustments |  | 40%
Time88 web application | App Suite Content Validation ¦ Reviewed app lineup, categories, icons, and content structure | 17:45 | 19:05 | 1h 20m | manager_approved | Validated 6 application cards and content mappings | Improved product positioning and application discoverability | Validation |  |  |  | 60%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Sketch App | Plan Card Visual Structure Enhancement ¦ Added folder tile, title hierarchy, and supporting project details | 10:00 | 11:15 | 1h 15m | manager_approved | Enhanced 3 card information elements | Improved card readability and made plan records easier to scan | Design |  |  |  | 50%
Sketch App | Plan Count and Sort Row Alignment ¦ Structured plan count and Recent sort control in one row | 11:30 | 13:10 | 1h 40m | manager_approved | Aligned 2 primary controls and added 1 visual divider | Improved information hierarchy and list navigation clarity | UI Refinement |  |  |  | 40%
Sketch App | Plan Listing Screen Reference Analysis ¦ Compared target left-side reference with current application output | 13:10 | 14:10 | 1h 0m | manager_approved | Reviewed 2 design outputs and identified key UI mismatches | Established clear redesign direction based on reference layout | Analysis |  |  |  | 60%
Sketch App | Divider and Section Separation ¦ Added divider below plan count and sort controls | 14:40 | 16:30 | 1h 50m | manager_approved | Implemented 1 section separator | Improved visual separation between controls and plan cards | Development |  | Invalid Compose padding combination caused compilation failure |  | 50%
Sketch App | Device-Based Visual Verification ¦ Run updated screen and compare against target reference | 16:30 | 17:30 | 1h 0m | manager_approved | Validate 10 modified UI elements on physical device | Will confirm actual icon sizing, spacing, alignment, and visual accuracy | Validation |  |  |  | 40%
Sketch App | Compose Padding Build Error Resolution ¦ Correct invalid Divider Modifier.padding implementation | 17:45 | 19:10 | 1h 25m | manager_approved | 1 compile-blocking syntax issue identified for correction | Root cause isolated to unsupported horizontal and bottom parameter combination | Bug Fixing |  |  |  | 60%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Sketch App | Status Filter Chip Redesign | 10:00 | 11:15 | 01:15 | draft | [6 empty] | 0%
Sketch App | Responsive Layout Validation | 11:30 | 13:10 | 01:40 | draft | [6 empty] | 0%
Sketch App | Project Subtitle Integration | 13:10 | 14:10 | 01:00 | draft | [6 empty] | 0%
Sketch App | Plan Listing Screen Reference Analysis | 14:40 | 16:30 | 01:50 | draft | [6 empty] | 0%
Sketch App | Device-Based Visual Verification | 16:30 | 17:30 | 01:00 | draft | [6 empty] | 0%
Sketch App | Compose Padding Build Error Resolution | 17:45 | 19:10 | 01:25 | draft | [6 empty] | 0%

## Samprakash
Timesheet Report — Samprakash ¦ July 6–10, 2026
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Phase 2 Restroom | Phase 2 Restroom | 15:00 | 16:00 | 01:00 | draft | [6 empty] | 0%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
BOQ software | Creation of new features and debugging | 12:30 | 13:30 | 01:00 | draft | [6 empty] | 0%

## Samyuktha
Timesheet Report — Samyuktha ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | Marked daily attendance for all employees ¦ ¦ Recorded and updated daily employee attendance in the system, ensuring accurate tracking of presence and leave , Noted EB meters for the day . | 10:00 | 10:20 | 0h 20m | manager_approved | Updated attendance for 14 employees on a daily basis. | Reduced discrepancies in attendance data. |  |  |  |  | 50%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution ¦ ¦ Executed the hiring process for the Site Engineer role by sourcing candidates, conducting screening, coordinating interviews, and supporting final selection to meet project requirements. | 10:20 | 11:50 | 1h 30m | manager_approved | 10 - site engineer profile | Supported the hiring process by identifying suitable profiles. | Calling and screening |  |  |  | 50%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution ¦ ¦ Managed talent acquisition activities for the Quantity Estimator role by sourcing candidates, conducting screening, coordinating interviews, and supporting the recruitment process to identify suitable candidates. | 11:50 | 13:20 | 1h 30m | manager_approved | 5 - quantity estimator hiring | Supported the hiring process by identifying suitable profiles. | Calling and screening |  |  |  | 50%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles ¦ ¦ Managed the offer process for the Purchase Assistant role by preparing offer letters, communicating employment terms, obtaining candidate acceptance, and coordinating pre-joining activities. | 13:20 | 14:00 | 0h 40m | manager_approved | 10 - purchase assistant profile | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Talent acquisition | Production Operator Candidate Sourcing ¦ ¦ Executed the recruitment process for the Production Operator role by sourcing candidates, conducting screening calls, coordinating interviews, and managing candidate follow-ups to fulfill the client company's hiring requirements. | 15:00 | 16:30 | 1h 30m | manager_approved | 5 - production operator | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring ¦ Analyze client requirements (language, experience, targets) ¦ Sourced and screened candidates for the client company's requirements at ISON Xperiences by identifying suitable profiles, conducting initial screening calls, and evaluating candidates based on job requirements and communication skills. | 16:30 | 18:00 | 1h 30m | manager_approved | 4 - lead generation executive | Supported the hiring process by identifying suitable profiles. | Source and collect candidate profiles - 150 |  |  |  | 50%
Pay sheet | Project entry and configuration in pms . ¦ ¦ Entered and configured project details in the PMS system, including project information, task assignments, milestones, and activity updates to ensure accurate project tracking and monitoring. | 18:00 | 19:00 | 1h 0m | manager_approved | Maintained accurate records for project tracking and reporting - 1 | Ensured accurate project setup and configuration in PMS | Update Time Strap |  | network issue |  | 50%
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | Marked daily attendance for all employees ¦ ¦ Recorded and updated daily employee attendance in the system, ensuring accurate tracking of presence and leave , Noted EB meters for the day . | 10:00 | 10:20 | 0h 20m | manager_approved | Updated attendance for 14 employees on a daily basis. | Reduced discrepancies in attendance data. |  |  |  |  | 50%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution ¦ ¦ Executed the hiring process for the Site Engineer role by sourcing candidates, conducting screening, coordinating interviews, and supporting final selection to meet project requirements. | 10:20 | 11:50 | 1h 30m | manager_approved | 10 - site engineer profile | Supported the hiring process by identifying suitable profiles. | Calling and screening |  |  |  | 50%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution ¦ ¦ Managed talent acquisition activities for the Quantity Estimator role by sourcing candidates, conducting screening, coordinating interviews, and supporting the recruitment process to identify suitable candidates. | 11:50 | 13:20 | 1h 30m | manager_approved | 10 - quantity estimator | Supported the hiring process by identifying suitable profiles. | Calling and screening |  |  |  | 50%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles ¦ ¦ Executed the recruitment process for the Purchase Assistant role by sourcing candidates, screening profiles, coordinating interviews, managing candidate follow-ups, and supporting offer rollout and onboarding activities. | 13:20 | 14:00 | 0h 40m | manager_approved | 5 - purchase assistant | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Talent acquisition | Production Operator Candidate Sourcing ¦ ¦ Executed the recruitment process for the Production Operator role by sourcing candidates, conducting screening calls, coordinating interviews, and managing candidate follow-ups to fulfill the client company's hiring requirements. | 14:40 | 16:30 | 1h 50m | manager_approved | 5 - production operator | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring ¦ Analyze client requirements (language, experience, targets) ¦ Managed the recruitment process for the client company ( Ison Xperience ) Voice Process requirement by sourcing candidates, conducting screening calls, coordinating interviews, and following up with candidates to ensure timely hiring. | 16:30 | 18:00 | 1h 30m | manager_approved | 5 - lead generation executive | Supported the hiring process by identifying suitable profiles. | Source and collect candidate profiles - 150 |  |  |  | 50%
Pay sheet | Project entry and configuration in pms . ¦ ¦ Entered and configured project details in the PMS (Project Management System), including project information, task allocation, timelines, and activity updates to ensure accurate project tracking and monitoring. | 18:00 | 19:00 | 1h 0m | manager_approved | Maintained accurate project records for tracking and reporting - 1 | Successfully configured project details in the PMS system | Update Time Strap |  |  |  | 50%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | Marked daily attendance for all employees ¦ ¦ Recorded and updated daily employee attendance in the system, ensuring accurate tracking of presence and leave , Noted EB meters for the day . | 10:00 | 10:20 | 0h 20m | manager_approved | Updated attendance for 14 employees on a daily basis. | Reduced discrepancies in attendance data. |  |  |  |  | 50%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution ¦ ¦ Executed the hiring process for the Site Engineer role by sourcing candidates, conducting screening, coordinating interviews, and supporting final selection to meet project requirements. | 10:20 | 11:50 | 1h 30m | manager_approved | 5 - site engineer profile | Supported the hiring process by identifying suitable profiles. | Calling and screening |  |  |  | 50%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution ¦ ¦ Managed talent acquisition activities for the Quantity Estimator role by sourcing candidates, conducting screening, coordinating interviews, and supporting the recruitment process to identify suitable candidates. | 11:50 | 13:20 | 1h 30m | manager_approved | 5 - quantity estimator hiring | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles ¦ ¦ Executed the recruitment process for the Purchase Assistant role by sourcing candidates, screening profiles, coordinating interviews, managing candidate follow-ups, and supporting offer rollout and onboarding activities. | 13:20 | 14:00 | 0h 40m | manager_approved | 7 - purchase assistant | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Talent acquisition | Production Operator Candidate Sourcing ¦ ¦ Executed the recruitment process for the Production Operator role by sourcing candidates, conducting screening calls, coordinating interviews, and managing candidate follow-ups to fulfill the client company's hiring requirements. | 14:50 | 16:30 | 1h 40m | manager_approved | 8 - production operator | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring ¦ Analyze client requirements (language, experience, targets) ¦ Sourced and screened candidates for the client company's requirements at ISON Xperiences by identifying suitable profiles, conducting initial screening calls, and evaluating candidates based on job requirements and communication skills. | 16:30 | 18:00 | 1h 30m | manager_approved | 5 - lead generation executive | Supported the hiring process by identifying suitable profiles. | Source and collect candidate profiles - 150 |  |  |  | 50%
Pay sheet | Edited the salary slips and sent them to all employees ¦ ¦ Entered and configured project details in the PMS (Project Management System), including project information, task allocation, timelines, and activity updates to ensure accurate project tracking and monitoring. | 18:00 | 19:10 | 1h 10m | manager_approved | Maintained accurate project records for tracking and reporting - 1 | Successfully configured project details in the PMS system | Update Time Strap |  |  |  | 50%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | Marked daily attendance for all employees ¦ ¦ Recorded and updated daily employee attendance in the system, ensuring accurate tracking of presence and leave , Noted EB meters for the day . | 09:50 | 10:10 | 0h 20m | manager_approved | Updated attendance for 14 employees on a daily basis. | Reduced discrepancies in attendance data. |  |  |  |  | 50%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution ¦ ¦ Executed the end-to-end recruitment process for the Site Engineer role by sourcing candidates, conducting initial screening, coordinating interviews, and supporting final selection to meet project requirements. | 10:10 | 11:40 | 1h 30m | manager_approved | 10 - site engineer profile | Supported the hiring process by identifying suitable profiles. | Calling and screening |  |  |  | 50%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution ¦ ¦ Managed the talent acquisition process for the Quantity Estimator role by sourcing candidates, screening resumes, conducting initial HR interviews, coordinating interviews with hiring managers, and following up with candidates to ensure timely recruitment. | 11:40 | 13:10 | 1h 30m | manager_approved | 5 - quantity estimator hiring and conducting the interview | Supported the hiring process by identifying suitable profiles. | Onboarding the candidates |  |  |  | 50%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles ¦ ¦ Executed the recruitment process for the Purchase Assistant role by sourcing candidates, screening profiles, coordinating interviews, managing candidate follow-ups, and supporting offer rollout and onboarding activities. | 13:10 | 14:00 | 0h 50m | manager_approved | 5 - purchase assistant | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Talent acquisition | Production Operator Candidate Sourcing ¦ ¦ Executed the recruitment process for the Production Operator role by sourcing candidates, conducting screening calls, coordinating interviews, and managing candidate follow-ups to fulfill the client company's hiring requirements. | 14:40 | 16:20 | 1h 40m | manager_approved | 6 - production operator | Supported the hiring process by identifying suitable profiles. | Sourcing |  |  |  | 50%
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring ¦ Analyze client requirements (language, experience, targets) ¦ Managed the recruitment process for the client company's Voice Process requirement by sourcing candidates, conducting screening calls, coordinating interviews, and following up with candidates to ensure timely hiring. | 16:20 | 17:50 | 1h 30m | manager_approved | 5 - lead generation executive | Supported the hiring process by identifying suitable profiles. | Source and collect candidate profiles - 150 |  |  |  | 50%
Pay sheet | Project entry and configuration in pms . ¦ ¦ Entered and configured project details in the PMS system, including project information, task assignments, milestones, and activity updates to ensure accurate project tracking and monitoring. | 17:50 | 19:00 | 1h 10m | manager_approved | Maintained accurate records for project tracking and reporting - 1 | Ensured accurate project setup and configuration in PMS | Update Time Strap |  |  |  | 50%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Pay sheet | Marked daily attendance for all employees | 10:00 | 10:20 | 00:20 | draft | [6 empty] | 0%
Site Engineer Hiring Initiative -100 | Site Engineer Recruitment Execution | 10:20 | 11:50 | 01:30 | draft | [6 empty] | 0%
Quantity Estimator Talent Acquisition - 50 | Quantity Estimator Hiring Execution | 11:50 | 13:20 | 01:30 | draft | [6 empty] | 0%
Purchase Assistant Talent Acquisition | End-to-End Recruitment for Purchase Assistant Roles | 13:20 | 14:00 | 00:40 | draft | [6 empty] | 0%
Talent acquisition | Production Operator Candidate Sourcing | 14:40 | 16:30 | 01:50 | draft | [6 empty] | 0%
Voice Process Hiring Campaign for Lead Generation - 50 Candidates - jun 26 | Candidate Sourcing, Screening & Interview Coordination for Voice Process Hiring | 16:30 | 18:00 | 01:30 | draft | [6 empty] | 0%
Pay sheet | Project entry and configuration in pms . | 18:00 | 19:10 | 01:10 | draft | [6 empty] | 0%

## Sivakumar
Timesheet Report — Sivakumar ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 10:15 | 12:15 | 02:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 12:15 | 14:15 | 02:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Buffing of the Existing walls already painted with emulsion upto 11 feet till the bare plastering is visible | 17:15 | 18:15 | 01:00 | draft | [6 empty] | 0%
Phase 2 Restroom | 250mm Depth Floor chasing for Laying Pipes inside the restroom | 19:15 | 19:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 19:45 | 20:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Chiseling of the existing walls upto 11 ft in order to lay wall tiles | 20:15 | 20:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Delivery of Sanitarywares and CP fittings | 20:45 | 21:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Delivery of Tiles | 21:15 | 21:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Excavation for Laying soil and waste water line upto 500mm depth | 21:45 | 22:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Excavation for Manhole chamber | 22:15 | 22:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Excavation required upto 1000mm | 22:45 | 23:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Manhole chamber Construction | 23:15 | 23:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Pest control | 23:45 | 23:59 | 00:14 | draft | [6 empty] | 0%
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Phase 2 Restroom | 250mm Depth Floor chasing for Laying Pipes inside the restroom | 17:15 | 17:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:45 | 18:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 18:15 | 18:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Concrete work | 19:15 | 19:45 | 00:30 | draft | [6 empty] | 0%
Customer Experience Centre Renovation | Acoustic Fabric Paneling | 19:45 | 20:15 | 00:30 | draft | [6 empty] | 0%
Customer Experience Centre Renovation | Plywood Support for TV | 20:15 | 20:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Removal of Balance soil from Parking Area | 20:45 | 21:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Side wall construction for Counters | 21:15 | 21:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Water Stagnation Test | 21:45 | 22:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Water Proofing | 22:15 | 22:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall Construction as per approved drawing | 22:45 | 23:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall Chesling | 23:15 | 23:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall Chasing for Plumbing works | 23:45 | 23:59 | 00:14 | draft | [6 empty] | 0%
Phase 2 Restroom | Rough Plastering | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall chasing for Electrical conduits | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Tile details for procurement Wall and Floor | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Shuttering work | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Sanitaryware and CP fittings sample approval | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:15 | 17:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 17:45 | 18:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 18:15 | 18:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Buffing of the Existing walls already painted with emulsion upto 11 feet till the bare plastering is visible | 18:45 | 19:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Create Items that are not part of BOQ - find qty and pricing | 19:15 | 19:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Delivery of Sanitarywares and CP fittings | 19:45 | 20:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Delivery of Tiles | 20:15 | 20:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Excavation required upto 1000mm | 20:45 | 21:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Getting Quotation details from vendor (pipes)-phase 2 | 21:15 | 21:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | PCC work after laying the floor concealed pipes | 21:45 | 22:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Pest control | 22:15 | 22:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Procurement of Sanitarywares and Fittings | 22:45 | 23:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | RCC laying underneath the floor cut area | 23:15 | 23:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Removal of Balance soil from Parking Area | 23:45 | 23:59 | 00:14 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall Chasing for Plumbing works | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Sanitaryware and CP fitting sample approval | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall Chesling | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Removal of existing AC ducts and closing all supply and return | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Rough Plastering | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:15 | 17:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 17:45 | 18:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Electrical Cable laying (power cables) | 18:45 | 19:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Electrical pipe laying | 19:15 | 19:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Excavation required upto 1000mm | 19:45 | 20:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Exhaust Ducts Installation | 20:15 | 20:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Filling of Soil | 20:45 | 21:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Filling Soil and Paver block Installation | 21:15 | 21:45 | 00:30 | draft | [6 empty] | 0%
EB 3 restroom renovation | Finalize the BOM for rest room project | 21:45 | 22:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Laminate Shade/Design Confirmation | 22:15 | 22:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Laying of inlet Pipe Line (Exterior) | 22:45 | 23:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Laying of Soil water line outside Restroom | 23:15 | 23:45 | 00:30 | draft | [6 empty] | 0%
Customer Care Experience Centre Addnl | Termination of Sockets and switches | 23:45 | 23:59 | 00:14 | draft | [6 empty] | 0%
Phase 2 Restroom | Tile details for procurement Wall and Floor | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall Chesling | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Wall Construction as per approved drawing | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Water Stagnation Test | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Water Proofing | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
SVP cabin | AC Power Installation | 17:15 | 17:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 17:45 | 18:15 | 00:30 | draft | [6 empty] | 0%
Hexaware restroom renovation | BOQ PREPARATION FOR RESTROOMS | 18:15 | 18:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Delivery of Sanitarywares and CP fittings | 18:45 | 19:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Delivery of Tiles | 19:15 | 19:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Electrical Cable laying (power cables) | 19:45 | 20:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Excavation required upto 1000mm | 20:15 | 20:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Excavation for Manhole chamber | 20:45 | 21:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Exhaust Ducts Installation | 21:15 | 21:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Filling of Soil | 21:45 | 22:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Laying of 160mm Pipe line | 22:15 | 22:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Laying of inlet Pipe Line (Exterior) | 22:45 | 23:15 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Laying of pipes of water Inlet | 23:15 | 23:45 | 00:30 | draft | [6 empty] | 0%
Phase 2 Restroom | Laying of Soil water line outside Restroom | 23:45 | 23:59 | 00:14 | draft | [6 empty] | 0%
Phase 2 Restroom | Shuttering for Slab for mounting the Granite top for Wash basin | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Manhole chamber Construction | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Pest control | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Rough Plastering | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Side wall construction for Counters | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%

## Sivaram C
Timesheet Report — Sivaram C ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
BOQ Products Adding | Create New Products for ¦ | 10:00 | 12:00 | 2h 0m | manager_approved | 6 | [5 empty] | 20%
BOQ Products Adding | Create New Products for Interior scope ¦ | 12:00 | 14:00 | 2h 0m | manager_approved | 6 |  | BOQ Products Creating Electrical |  |  |  | 20%
DLF | Get Material Details from Vendor ¦ | 14:00 | 15:30 | 1h 30m | pending | 6 | [5 empty] | 30%
DLF | Get Material and Labour Pricing from Vendors ¦ | 14:30 | 15:00 | 0h 30m | manager_approved | 6 | [5 empty] | 20%
BOQ Products Materials Creation | Given Excel Material Adding BOQ ¦ Panelling Product Creating to BOQ | 15:30 | 16:30 | 1h 0m | manager_approved | 6 |  | Creating New Products in BOQ |  |  |  | 20%
DLF | Get Material and Labour Pricing from Vendors ¦ | 17:00 | 19:00 | 2h 0m | manager_approved | 6 | [5 empty] | 20%
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
BOQ Products Adding | Create New Products for ¦ | 10:30 | 11:00 | 0h 30m | manager_approved | 6 |  | BOQ Products Creating for Interior works |  |  |  | 20%
DLF | Get Material and Labour Pricing from Vendors ¦ | 14:00 | 15:00 | 1h 0m | manager_approved | 6 |  | Proposal to Client |  |  |  | 20%
DLF | Get Material Details from Vendor ¦ | 15:00 | 16:00 | 1h 0m | manager_approved | 6 |  | Proposal to Client |  |  |  | 20%
DLF | Prepare BOM ¦ | 16:00 | 17:00 | 1h 0m | manager_approved | 3 |  | Proposal to Client |  |  |  | 20%
DLF | Prepare BOQ ¦ | 17:00 | 18:00 | 1h 0m | manager_approved | 6 |  | Proposal to Client |  |  |  | 30%
BOQ Products Adding | Create New Products for Interior scope ¦ | 18:00 | 19:00 | 1h 0m | manager_approved | 6 | [5 empty] | 20%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
BOQ Products Materials Creation | Prepare BOM ¦ | 10:30 | 11:00 | 0h 30m | manager_approved | 6 | [5 empty] | 20%
BOQ Products Materials Creation | Given Excel Material Adding BOQ ¦ Panelling Product Creating to BOQ ¦ Add the New project BOQ in the materials and Products | 11:00 | 12:00 | 1h 0m | manager_approved | 3 | Completed deviation BOQ calculations. | Creating New Products in BOQ |  |  |  | 30%
BOQ Products Materials Creation | Get Material Details from Vendor ¦ | 12:00 | 13:00 | 1h 0m | manager_approved | 6 |  | Learn BOM Generate |  |  |  | 20%
BOQ Products Materials Creation | Get Material and Labour Pricing from Vendors ¦ | 14:00 | 15:00 | 1h 0m | manager_approved | 6 |  | Proposal to Client |  |  |  | 20%
BOQ Products Materials Creation | add new products ¦ | 15:00 | 16:00 | 1h 0m | manager_approved | 6 |  | Adding Door Materials to BOQ |  |  |  | 20%
BOQ Products Adding | Prepare BOQ ¦ | 16:00 | 17:00 | 1h 0m | manager_approved | 6 |  | BOQ Products Creating for Interior works |  |  |  | 20%
BOQ Products Adding | Prepare BOM ¦ | 17:00 | 18:00 | 1h 0m | manager_approved | 5 |  | BOQ Products Creating Electrical |  |  |  | 30%
BOQ Products Adding | Create New Products for ¦ | 18:00 | 19:00 | 1h 0m | manager_approved | 6 |  | BOQ Products Creating for Interior works |  |  |  | 20%
BOQ Products Adding | Get Material and Labour Pricing from Vendors ¦ | 19:00 | 20:00 | 1h 0m | manager_approved | 6 | [5 empty] | 40%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
CRECHE | Get Material and Labour Pricing from Vendors | 10:00 | 14:00 | 04:00 | draft | [6 empty] | 0%
CRECHE | Get Material Details from Vendor | 17:45 | 18:15 | 00:30 | draft | [6 empty] | 0%
CRECHE | Prepare BOM | 18:15 | 18:45 | 00:30 | draft | [6 empty] | 0%
CRECHE | Prepare BOQ | 18:45 | 19:15 | 00:30 | draft | [6 empty] | 0%
BOQ Products Adding | Create New Products for | 19:15 | 19:45 | 00:30 | draft | [6 empty] | 0%
BOQ Products Adding | Create New Products for Interior scope | 19:45 | 20:15 | 00:30 | draft | [6 empty] | 0%
BOQ Products Adding | Get Material and Labour Pricing from Vendors | 20:15 | 20:45 | 00:30 | draft | [6 empty] | 0%
BOQ Products Adding | Get Material Details from Vendor | 20:45 | 21:15 | 00:30 | draft | [6 empty] | 0%
BOQ Products Adding | Prepare BOM | 21:15 | 21:45 | 00:30 | draft | [6 empty] | 0%
BOQ Products Adding | Prepare BOQ | 21:45 | 22:15 | 00:30 | draft | [6 empty] | 0%
BOQ Products Materials Creation | Get Material Details from Vendor | 22:15 | 22:45 | 00:30 | draft | [6 empty] | 0%
BOQ Products Materials Creation | Given Excel Material Adding BOQ | 22:45 | 23:15 | 00:30 | draft | [6 empty] | 0%
BOQ Products Materials Creation | Materials collecting from AI | 23:15 | 23:45 | 00:30 | draft | [6 empty] | 0%
BOQ Products Materials Creation | Prepare BOM | 23:45 | 23:59 | 00:14 | draft | [6 empty] | 0%
BOQ Products Materials Creation | Prepare BOQ | 23:59 | 23:59 | 00:00 | draft | [6 empty] | 0%

## Yuvaraj
Timesheet Report — Yuvaraj ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film ¦ | 10:00 | 12:30 | 2h 30m | manager_approved | on process | [5 empty] | 10%
Phase 2 Restroom | Bison Board fixing to close Glass Partition ¦ | 12:30 | 14:03 | 1h 33m | manager_approved | on process | [5 empty] | 10%
General project | General task ¦ | 14:30 | 15:30 | 1h 0m | manager_approved | on process | [5 empty] | 10%
Store Room Modificatoin at Featherlite | Get Material and Labour Pricing from Vendors ¦ | 15:30 | 17:00 | 1h 30m | manager_approved | on process | [5 empty] | 10%
Store Room Modificatoin at Featherlite | Get Material Details from Vendor ¦ | 17:00 | 18:00 | 1h 0m | manager_approved | on process | [5 empty] | 10%
CTI Maintenance | Material pricing and arrangements ¦ | 18:00 | 19:00 | 1h 0m | manager_approved | on process | [5 empty] | 10%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Phase 2 Restroom | All Wall Construction, Main door, Restroom walls, Passage walls, Demolished walls along with Lintel at 3 feet and 7 feet | 08:30 | 12:30 | 04:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison board installation on the exterior glass side wall. Includes frost film | 12:30 | 14:00 | 01:30 | draft | [6 empty] | 0%
SVP cabin | all interior work | 14:30 | 18:30 | 04:00 | draft | [6 empty] | 0%
Phase 2 Restroom | Bison Board fixing to close Glass Partition | 17:15 | 17:45 | 00:30 | draft | [6 empty] | 0%

## Zameela Begam
Timesheet Report — Zameela Begam ¦ July 6–10, 2026
📅 Monday, July 6
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 ¦ ¦ Analyzed and updated the CTI 2025–26 monthly provision Excel sheet, verifying calculations and financial figures to maintain accurate records. | 10:20 | 11:15 | 0h 55m | manager_approved | 1 month | Successfully analyzed and updated the monthly provision Excel sheet for CTI 2025–26 to ensure accurate financial data alignment for the month. |  |  |  |  | 70%
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses ¦ ¦ Successfully reconciled and updated the clarified excel workings with Zoho Expenses to ensure accurate documentation for the IT Filing CTI 2025–26. | 11:30 | 14:05 | 2h 35m | manager_approved | 5 Employees Advance Reconciliation | Cross-verified and updated Zoho Expenses data against the clarified excel workings spreadsheet to prepare documentation required for the IT filing process. | Analysis & update of Zoho expenses |  |  |  | 60%
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing ¦ ¦ Processed vendor reconciliation and verified account recordings for 9 sundry creditor ledger accounts under the CTI 2025-26 project. | 14:35 | 17:25 | 2h 50m | manager_approved | 9 Ledger Accounts | Successfully verified and reconciled 9 sundry creditor ledger accounts to ensure accurate financial tracking for the CTI 2025-26 project. |  |  |  |  | 30%
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing ¦ ¦ Conducted ledger verification and account recording reviews for Ganesh Electricals & Hardware under the Sundry Creditors CTI 2025-26 project scope. | 17:40 | 18:50 | 1h 10m | manager_approved | 1 ledger - Ganesh Electricals & Hardware | Successfully verified and reconciled the sundry creditor ledger account for Ganesh Electricals & Hardware to ensure accurate financial tracking for the CTI 2025-26 project | Verifying recordings of sundry creditors accounts |  |  |  | 70%
📅 Tuesday, July 7
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
TDS FILING FY2026-27 | Pan & bills verification for Jun 2026 CTI ¦ ¦ Completed the thorough verification of 17 vendor bills and 9 PAN cards for June 2026 to ensure accurate data for the upcoming TDS filing. | 09:50 | 11:15 | 1h 25m | manager_approved | 17 bills & 9 PAN Card | Verified 17 vendor bills and 9 PAN cards for June 2026 to ensure proper documentation and accurate excel calculations for TDS filing FY2026-27. | Documentation & excel workings |  |  |  | 98%
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses ¦ ¦ Verified Zoho expenses data and updated clarified Excel workings for 14 employees to support the IT filing process. ( 2 PO and 1 Bill drafted ) | 11:20 | 14:30 | 3h 10m | manager_approved | 14 employees verified | Successfully verified Zoho expenses and clarified Excel working sheets for 14 employees to ensure precise data alignment for IT filing. |  |  |  |  | 60%
IT Filing CTI 2025-26 | Coordination with IT filing CTI ¦ ¦ Coordinated with the IT filing team to clarify compliance requirements and resolve open points for 6 ledgers under the CTI project. ( 2 PO & 1 Bill drafted ) | 14:00 | 17:05 | 3h 5m | manager_approved | 6 ledgers | Successfully coordinated with the IT filing team and clarified requirements for 6 ledgers to ensure accurate data alignment for the IT filing FY2025-26. | Filing & requirement Clarification |  |  |  | 30%
IT Filing CTI 2025-26 | Coordination with IT filing CTI ¦ ¦ Successfully coordinated with the IT filing team and clarified requirements for 6 ledgers to ensure accurate data alignment for the IT filing FY2025-26. ( Meeting with SGK Monica Auditing staff ) | 17:05 | 17:45 | 0h 40m | manager_approved | 6 ledger accounts | Coordinated with the IT filing team to clarify compliance requirements and resolve open points for 6 ledgers under the CTI project. |  |  |  |  | 6%
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses ¦ ¦ Analyzed, updated, and clarified the 1-year expense Excel workings against Zoho Expenses data to prepare accurate documentation for the IT filing. | 18:05 | 18:50 | 0h 45m | manager_approved | 1 year expense excel | Successfully analyzed and updated the 1-year expense Excel sheet, clarifying all workings with Zoho Expenses to ensure accurate data alignment for the IT filing. | Analysis & update of Zoho expenses |  |  |  | 50%
📅 Wednesday, July 8
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses ¦ ¦ Completed a detailed 1-year Excel analysis and comparison of 2 quotes, updating and aligning all relevant Zoho expenses for the IT Filing CTI 2025–26. | 09:45 | 11:15 | 1h 30m | manager_approved | 1 year excel & comparison of 2 quotes | Analyzed and updated Zoho expenses related to the IT Filing CTI 2025–26. | Analysis & update of Zoho expenses |  |  |  | 60%
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing ¦ ¦ Verified 12 sundry creditor account ledgers under the CTI 2025-26 project, ensuring all recording entries are accurate and reconciled. | 11:30 | 14:15 | 2h 45m | pending | 12 ledgers verified | Verified and validated 12 sundry creditor ledgers for CTI 2025-26 to ensure accurate recording. |  |  |  |  | 23%
IT Filing CTI 2025-26 | Coordination with IT filing CTI ¦ ¦ Managed the coordination for CTI 2025-26 IT filing, focusing on the analysis, update, and verification of 12 corporate expense ledgers within Zoho. | 14:45 | 17:15 | 2h 30m | manager_approved | 12 ledgers verified | Verified 12 detailed ledgers and coordinated effectively with the IT filing team for CTI 2025-26 to ensure error-free data alignment. | Analysis & update of Zoho expenses |  |  |  | 30%
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 ¦ ¦ Conducted a detailed analysis and update of the CTI 2025-26 monthly provision Excel sheet, incorporating a comprehensive comparison of five vendor proposals. | 17:30 | 19:15 | 1h 45m | manager_approved | 3 Months & Comparison of 5 vendors | Analyzed 3 months of monthly provision data and successfully compared pricing/terms across 5 different vendors to optimize project costs. | Analysis & update |  |  |  | 30%
📅 Thursday, July 9
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 ¦ ¦ Successfully analyzed and updated the monthly financial provisions for a 3-month period, ensuring accurate tracking and reconciliation of the data within the master Excel model. | 09:45 | 11:15 | 1h 30m | manager_approved | 3 month | Conducted a detailed analysis and update of the monthly provision Excel sheet for a 3-month period to maintain accurate financial records and verification details. | Verification of Provision details |  |  |  | 70%
Oracle Fusion | Registration Proceeding of HTL India - Hexaware ¦ ¦ Managed the supplier registration proceedings for HTL India and Hexaware in Oracle Fusion, successfully completing the documentation and setup in both companies | 11:30 | 14:15 | 2h 45m | manager_approved | 2 companies registration | Successfully initiated and advanced the supplier registration proceedings in HTL India and Hexaware within Oracle Fusion, resulting in the successful registration setup for 2 companies. |  |  |  |  | 80%
Oracle Fusion | Registration Proceeding of HTL India - Hexaware ¦ ¦ Processed 2 supplier registrations in Oracle Fusion and developed a detailed Excel comparison model for 5 vendor quotes to support procurement and cost evaluation. | 14:45 | 16:30 | 1h 45m | manager_approved | 2 registration completion & 5 quote comparison excel | Completed 2 supplier registrations in Oracle Fusion and prepared a comprehensive Excel sheet comparing 5 vendor quotes to streamline procurement decisions. | Supplier Registration |  |  |  | 99%
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses ¦ ¦ a comprehensive analysis and update of Zoho expenses by generating a detailed 1-year expense Excel sheet to ensure clear financial tracking and reconciliation. | 16:30 | 17:30 | 1h 0m | manager_approved | 1 year expense excel | Generated and updated a 1-year expense Excel sheet based on Zoho expense data to ensure precise documentation and clear financial breakdown for IT filing. | Analysis & update of Zoho expenses |  |  |  | 20%
Bike Insurance | Evaluation & Confirmation of Quote for Bike Insurance ¦ ¦ Successfully collected, reviewed and evaluated 6 different bike insurance quotes to compare coverage features and negotiate key policy terms. ( Discussion with Sam sir ) | 17:45 | 18:50 | 1h 5m | manager_approved | 6 quotes | Evaluated and compared 6 bike insurance quotes, analyzing key features and negotiating coverage terms to finalize the best policy option. |  |  |  |  | 88%
📅 Friday, July 10
Project | Task | Start | End | Hours | Status | Quantify | Achievements | Key Step | Tools Used | Problems/Issues | Scope of Improvements | % Complete
Monthly Provision 2026-27 | Analysis & update of monthly provision excel CTI 2025-26 | 10:00 | 11:15 | 01:15 | draft | [6 empty] | 0%
Bike Insurance | Evaluation & Confirmation of Quote for Bike Insurance | 11:30 | 12:00 | 00:30 | draft | [6 empty] | 0%
Vendor Bills Reconciliation 2026-27 | Reconciliation of vendor bills against Zoho books Apr-May 2026 | 12:00 | 13:00 | 01:00 | draft | [6 empty] | 0%
IT Filing CTI 2025-26 | Clarified workings excel - Zoho Expenses | 13:00 | 14:05 | 01:05 | draft | [6 empty] | 0%
Sundry Creditors - CTI 2025-26 | Vendor Reconciliation Processing | 14:35 | 17:15 | 02:40 | draft | [6 empty] | 0%
IT Filing CTI 2025-26 | Coordination with IT filing CTI | 17:30 | 19:00 | 01:30 | draft | [6 empty] | 0%