## Overdue Tasks
Project | Task | Assigned To | Priority | Progress% | Due Date | Days Overdue | Status
Senior VP Cabin Revamp | Get CAD and PDF Layour |  | medium | 0% | 2026-02-09 | 115 | pending
Senior VP Cabin Revamp | Site Visit |  | medium | 0% | 2026-02-09 | 115 | pending
Reception Revamp | Material pricing | YUVARAJ S | high | 0% | 2026-02-12 | 112 | pending
Canteen Renovation | 3D Drawing approval |  | medium | 0% | 2026-02-12 | 112 | pending
MD Cabin and Other cabin Upgrade - Sysarc | get me pricing for Motorized Blinds |  | medium | 0% | 2026-02-12 | 112 | pending
Carpay ODC | Create BOQ | SIVARAM C | medium | 0% | 2026-02-13 | 111 | On Hold
Carpay ODC | Create Scope | SAM | medium | 0% | 2026-02-13 | 111 | pending
Carpay ODC | Compile Pricing and Create a BOM | SIVARAM C | medium | 0% | 2026-02-14 | 110 | In Progress
Carpay ODC | Get Vendor Quotes | SIVARAM C | medium | 0% | 2026-02-14 | 110 | On Hold
EB3 LIFT GLASS REPLACEMENT | Execution |  | medium | 0% | 2026-02-15 | 109 | Planned
Carpay ODC | Create Proposal and send it to Client | SAM | medium | 0% | 2026-02-16 | 108 | pending
False Ceiling at Hexaveristy | send Proposal to Client |  | medium | 0% | 2026-02-20 | 104 | In Progress
False Ceiling at Hexaveristy | Verify Proposal | SAM | medium | 0% | 2026-02-25 | 99 | pending
BOQ Products Adding | Create New Products for |  | medium | 0% | 2026-03-04 | 92 | pending
Canteen Renovation | iiii |  | medium | 0% | 2026-03-04 | 92 | Not Started
Restroom Cubicle | Get Revised Proposal from Vendor | YUVARAJ S | medium | 0% | 2026-03-04 | 92 | pending
Marble Remoal and Refixing at Phase 2 | Marble Requirement | ARUN KUMAR V | medium | 0% | 2026-03-05 | 91 | pending
Marble Remoal and Refixing at Phase 2 | Get Quotes and update in BOQ software | ARUN KUMAR V | high | 0% | 2026-03-05 | 91 | pending
Marble Remoal and Refixing at Phase 2 | Get Quotes and update in BOQ software | YUVARAJ S | high | 0% | 2026-03-05 | 91 | pending
Marble Remoal and Refixing at Phase 2 | Marble Requirement | YUVARAJ S | medium | 0% | 2026-03-05 | 91 | pending
BOQ Products Adding | Create New Products for Interior scope |  | medium | 0% | 2026-03-05 | 91 | pending
Madipakkam Home Repair work | Fix New door at site with existing hardware | SIVARAM C | medium | 0% | 2026-03-08 | 88 | pending
Madipakkam Home Repair work | Fix New door at site with existing hardware | RANJITH | medium | 0% | 2026-03-08 | 88 | pending
BOQ Products Materials Creation | Given Excel Material Adding BOQ |  | medium | 0% | 2026-03-09 | 87 | in-progress
BOQ Products Materials Creation | Materials collecting from AI |  | medium | 0% | 2026-03-14 | 82 | pending
False Ceiling Revamp - Wood | Meeting with client to discuss on the requirement | SAM | medium | 0% | 2026-03-31 | 65 | pending
library project | Removing and shifting work start date ? | RANJITH | medium | 0% | 2026-03-31 | 65 | On Hold
library project | Removing and shifting work start date ? | SAM | medium | 0% | 2026-03-31 | 65 | On Hold
World Bank ODC | Prepare BOM | SIVARAM C | medium | 0% | 2026-04-07 | 58 | On Hold
test | test demo |  | medium | 0% | 2026-04-30 | 35 | in-progress
Carpet at Passage For Wood | Prepare BOQ and send to client | SAM | medium | 0% | 2026-05-18 | 17 | pending
Repair and Maintenance at Wood - May 26 | Delivery of Tiles at Site |  | medium | 0% | 2026-05-19 | 16 | pending
House Keeping Services | Get alternate agencies pricing for the requirements |  | medium | 0% | 2026-05-19 | 16 | Not Started
Repair and Maintenance at Wood - May 26 | Refixing of Existing Workstation |  | medium | 0% | 2026-05-20 | 15 | pending
Wood Grid Ceiling Repair | Prepare sketch a plan and BOM | SIVARAM C | medium | 0% | 2026-05-21 | 14 | pending
House Keeping Services | Provide Evaluation report of all vendors |  | medium | 0% | 2026-05-21 | 14 | Not Started
Repair and Maintenance at Wood - May 26 | Prepare BOM | SIVARAM C | medium | 0% | 2026-05-23 | 12 | pending
Tambaram Home Renovation | Get Pricing for Both Rental and Procurement option | ARUN KUMAR V | medium | 10% | 2026-05-26 | 9 | In Progress
Raw water Plumbing line change from EB3 to EB2 | Get Material and Labour Pricing from Vendors | ARUN KUMAR V | medium | 10% | 2026-05-26 | 9 | In Progress
Tambaram Home Renovation | Get Pricing for Both Rental and Procurement option | YUVARAJ S | medium | 10% | 2026-05-26 | 9 | In Progress
Raw water Plumbing line change from EB3 to EB2 | Get Material and Labour Pricing from Vendors | YUVARAJ S | medium | 10% | 2026-05-26 | 9 | In Progress
EB 3 restroom renovation | Prepare BOM | SIVARAM C | medium | 0% | 2026-05-27 | 8 | In Progress
Marble Electrical work | Update Pricing Mentioning Project Pricing | ARUN KUMAR V | medium | 0% | 2026-05-27 | 8 | In Progress
Marble Electrical work | Update Pricing Mentioning Project Pricing | YUVARAJ S | medium | 0% | 2026-05-27 | 8 | In Progress
100" TV and Storage unit - Lumina | Prepare BOQ | SAM | medium | 0% | 2026-05-27 | 8 | pending
Marble Electrical work | Need 3 quotes for all Electrical Materials | SIVARAM C | medium | 0% | 2026-05-27 | 8 | In Progress
Marble Electrical work | Need 3 quotes for all Electrical Materials | ARUN KUMAR V | medium | 0% | 2026-05-27 | 8 | In Progress
Marble Electrical work | Need 3 quotes for all Electrical Materials | YUVARAJ S | medium | 0% | 2026-05-27 | 8 | In Progress
100" TV and Storage unit - Lumina | Prepare BOM | SIVARAM C | medium | 0% | 2026-05-27 | 8 | pending
EB 3 restroom renovation | Prepare BOM | Sivakumar | medium | 0% | 2026-05-27 | 8 | In Progress
100" TV and Storage unit - Lumina | Get Material and Labour Pricing | ARUN KUMAR V | medium | 0% | 2026-05-27 | 8 | In Progress
100" TV and Storage unit - Lumina | Get Material and Labour Pricing | YUVARAJ S | medium | 0% | 2026-05-27 | 8 | In Progress
100" TV and Storage unit - Lumina | Get Material and Labour Pricing | SIVARAM C | medium | 0% | 2026-05-27 | 8 | In Progress
EB 3 restroom renovation | Prepare BOQ |  | medium | 0% | 2026-05-28 | 7 | pending
Solar Panel Installation | Get Pricing from Vendor | YUVARAJ S | medium | 0% | 2026-05-28 | 7 | pending
Solar Panel Installation | Prepare BOM | SIVARAM C | medium | 0% | 2026-05-28 | 7 | pending
EB 3 restroom renovation | Get Pricing for All Materials and Labours | ARUN KUMAR V | medium | 10% | 2026-05-28 | 7 | In Progress
EB 3 restroom renovation | Get Pricing for All Materials and Labours | YUVARAJ S | medium | 10% | 2026-05-28 | 7 | In Progress
Sales invoice Raising 2026-27 | Verification of invoices & confirmation of Hexaware PO | MOHAN RAJ C | medium | 90% | 2026-05-28 | 7 | In Progress
Sales invoice Raising 2026-27 | Verification of invoices & confirmation of Hexaware PO | ZAMEELA BEGAM N | medium | 90% | 2026-05-28 | 7 | In Progress
Customer Experience Centre Renovation | Get Material and Labour Pricing from Vendors |  | medium | 0% | 2026-05-28 | 7 | pending
Customer Experience Centre Renovation | Get Material Details from Vendor |  | medium | 0% | 2026-05-28 | 7 | pending
Customer Experience Centre Renovation | Prepare BOQ |  | medium | 0% | 2026-05-28 | 7 | pending
Customer Experience Centre Renovation | Prepare BOM |  | medium | 0% | 2026-05-28 | 7 | pending
Dalmia Cements - 4th Floor Renovation | Cost Comparison between vendors and different Packages | YUVARAJ S | medium | 0% | 2026-05-29 | 6 | pending
Dalmia Cements - 4th Floor Renovation | Create BOQ | MOHAN RAJ C | medium | 95% | 2026-05-29 | 6 | In Progress
Dalmia Cements - 4th Floor Renovation | Get Material and Labour Cost | YUVARAJ S | medium | 0% | 2026-05-29 | 6 | pending
Solar Panel Installation | Prepare BOQ | SAM | medium | 0% | 2026-05-29 | 6 | pending
Tiles Laying - Next | Get from KVP | ARUN KUMAR V | medium | 0% | 2026-05-29 | 6 | pending
Tiles Laying - Next | Get from KVP | YUVARAJ S | medium | 0% | 2026-05-29 | 6 | pending
Tiles Laying - Next | Get from Manoj | Sivakumar | medium | 0% | 2026-05-29 | 6 | pending
Tiles Laying - Next | Get from Sunil | Sivakumar | medium | 0% | 2026-05-29 | 6 | pending
Time strap Upgrade | Creation of new features | Rebecasuji.A | medium | 31% | 2026-05-30 | 5 | In Progress
HR Operations | Meeting with sam sir | Samyuktha S | medium | 30% | 2026-05-30 | 5 | In Progress
Bank Statement reconciliation CTI ICICI 2025-26 | Updating Entries in Zoho Books CTI ICICI 2025-26 | ZAMEELA BEGAM N | high | 80% | 2026-05-30 | 5 | In Progress
Bank Statement reconciliation CTI ICICI 2025-26 | Updating Entries in Zoho Books CTI ICICI 2025-26 | MOHAN RAJ C | high | 80% | 2026-05-30 | 5 | In Progress
Bank Statement reconciliation CTI HDFC 2025-26 | Updating entries as per Bank Statement 2025-26 |  | high | 80% | 2026-05-30 | 5 | In Progress
HR Operations | Meeting with sam sir | P PUSHPA | medium | 30% | 2026-05-30 | 5 | In Progress
Time strap Upgrade | Creation of new features | DurgaDevi E | medium | 31% | 2026-05-30 | 5 | In Progress
Dalmia Cements - 4th Floor Renovation | Proposal upload in Ariba |  | medium | 0% | 2026-05-31 | 4 | pending
Time strap Upgrade | Designing architecture of the agent .exe and working |  | medium | 0% | 2026-05-31 | 4 | pending
Time strap Upgrade | Development of Desktop Agent | Rebecasuji.A | medium | 46% | 2026-05-31 | 4 | In Progress
Time strap Upgrade | Development of Desktop Agent | DurgaDevi E | medium | 46% | 2026-05-31 | 4 | In Progress
Pending Payment Follow Up - 2025-26 | Follow up call - Sampath | ZAMEELA BEGAM N | medium | 0% | 2026-05-31 | 4 | in-progress
Pending Payment Follow Up - 2025-26 | Follow up call - Sampath | MOHAN RAJ C | medium | 0% | 2026-05-31 | 4 | in-progress
Financial Policies Creation | Drafting of financial policies with compliances CTI 2026 | MOHAN RAJ C | medium | 70% | 2026-06-02 | 2 | In Progress
Vendor Bills Reconciliation 2026-27 | Kumaran Accounts Reconciliation 19/6/2025 to 12/5/2026 | MOHAN RAJ C | medium | 95% | 2026-06-02 | 2 | In Progress
Financial Policies Creation | Drafting of financial policies with compliances CTI 2026 | ZAMEELA BEGAM N | medium | 70% | 2026-06-02 | 2 | In Progress
Vendor Bills Reconciliation 2026-27 | Kumaran Accounts Reconciliation 19/6/2025 to 12/5/2026 | ZAMEELA BEGAM N | medium | 95% | 2026-06-02 | 2 | In Progress
Aspire Systems | Aspire - Quotation | MOHAN RAJ C | medium | 95% | 2026-06-03 | 1 | In Progress
Cafeteria Modification | Create Auto Cad Floor Drawings | SAM | medium | 0% | 2026-06-03 | 1 | in-progress
Sales invoice Raising 2026-27 | Verification of KVP Constructions Measurement sheet | ZAMEELA BEGAM N | medium | 80% | 2026-06-03 | 1 | In Progress
HR Operations | Exit Form Preparation and Invoice Follow-up | Samyuktha S | medium | 30% | 2026-06-03 | 1 | in-progress
HR Operations | Exit Form Preparation and Invoice Follow-up | P PUSHPA | medium | 30% | 2026-06-03 | 1 | in-progress
Hexaware restroom renovation | BOQ PREPARATION FOR RESTROOMS | YUVARAJ S | high | 0% | 2026-06-03 | 1 | in-progress